## SHIP
MORE HOMES DIVISION
HARP Ref | Project Name | Town | LHS Area | HMA | Developer | Landlord | SG Tender Approval Year | SG Approval Month | Total Unit Numbers | General Needs Units | Specific Needs Units | Wheelchair Units | TOTAL GN Units | GN - 1 bed | GN - 2 bed | GN - 3 bed | GN - 4 bed | GN - 5 bed | GN - 6+ bed | TOTAL SN Units | SN - 1 bed | SN - 2 bed | SN - 3 bed | SN - 4 bed | SN - 5 bed | SN - 6+ bed | TOTAL Wheelchair Units | WC - 1 bed | WC - 2 bed | WC - 3 bed | WC - 4 bed | WC - 5 bed | WC - 6+ bed | % SN Units | % Wheelchair Units | Tenure | Est/Actual site start year | Est/Actual site start month | Est/Actual Comp Year | Est/Actual Comp Month | SG Grant Pre 2020/2021 (£m) | SG Grant 2021/2022 (£m) | SG Grant 2022/2023 (£m) | SG Grant 2023/2024 (£m) | SG Grant 2024/2025 (£m) | SG Grant 2025/2026 (£m) | SG Grant Post 2025/2026 (£m) | Total SG Funding | Total 2HCT (£m) | Total FC Commuted Sums (£m) | Communted Sums Long Stop Date | Total Subsidy (£m) | Total Subsidy per unit (£m) | SHIP HMA Need | SHIP LHSA Need | SHIP Devt- Planning & Land | SHIP Devt Status (RAG) | SHIP SF - Equualities | SHIP SF - Wider Objectives | SHIP Housing Need Total | SHIP Devt Total | SHIP SF Total | SHIP Total | Comment
P43211 | Aberdour Road | Aberdour | Dunfermline & Coast | Dunfermline & West | KHA | KHA | 2022/23 | July | 21 | 15 | 6 |  | 15 |  | 6 | 9 |  |  |  | 6 |  | 6 |  |  |  |  | 0 | [6 empty] | 28.57% | 0% | SR | 2022/23 | July | 2023/24 | July |  |  | 1.596 |  |  |  |  | 1.596 |  |  |  | 1.596 | 0.076 | 40 | 45 | 40 | 70 | 0 | 0 | 85 | 110 | 0 | 195
P43380 | Ladywalk (Former Care Home) | Anstruther | Largo & East Neuk | St Andrews & North East | FC | FC | 2024/25 | September | 10 | 7 | 2 | 1 | 5 | 0 | 2 | 2 | 1 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 20% | SR | 2024/25 | September | 2025/26 | August |  |  |  |  | 0.59 |  |  | 0.59 |  |  |  | 0.59 | 0.059 | 30 | 30 | 50 | 10 | 0 | 0 | 60 | 60 | 0 | 120
P43379 | Mayview Court (New Care Village) | Anstruther | Largo & East Neuk | St Andrews & North East | FC | FC | 2022/23 | January | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 12 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | 2022/23 | January | 2024/25 | June |  |  | 0.1 | 0.726 | 0.28 |  |  | 1.106 |  |  |  | 1.106 | 0.079 | 30 | 30 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180
P43195 | Carswell Wynd | Auchtermuchty | Cupar & HOF | Cupar & North West | KHA | KHA | 2024/25 | December | 49 | 32 | 16 | 1 | 40 |  | 21 | 8 |  |  |  | 8 |  | 14 | 2 | 2 |  |  | 1 |  | 1 | 1 |  |  |  | 34.69% | 2.041% | SR | 2024/25 | December | 2025/26 | March |  |  |  |  | 1 | 2.822 |  | 3.822 |  |  |  | 3.822 | 0.078 | 20 | 15 | 0 | 10 | 0 | 0 | 35 | 10 | 0 | 45
P43396 | Kirkland Farm Phase 3 | Ballingry | Cowdenbeath | Dunfermline & West | KHA | KHA | 2019/20 | March | 63 | 51 | 12 | 0 | 51 |  | 30 | 21 |  |  |  | 12 |  | 6 |  | 6 |  |  | 0 | [6 empty] | 19.05% | 0% | SR | 2019/20 | March | 2022/23 | April | 3.566 | 1.437 | [5 empty] | 5.003 |  |  |  | 5.003 | 0.079413 | 40 | 25 | 80 | 70 | 0 | 0 | 65 | 150 | 0 | 215
P41440 | Main Street | Ballmulo | St Andrews | St Andrews & North East | KHA | KHA | 2021/22 | May | 15 | 9 | 6 | 0 | 9 |  | 9 |  |  |  |  | 6 |  | 5 |  | 1 |  |  | 0 | [6 empty] | 40% | 0% | SR | 2021/22 | June | 2021/22 | March | 0.125 | 1.045 | [5 empty] | 1.17 |  |  |  | 1.17 | 0.078 | 30 | 50 | 10 | 30 | 0 | 0 | 80 | 40 | 0 | 120
P44701 | South Avenue (South) | Blairhall | West Fife Villages | Dunfermline & West | FC PSD | FC | 2021/22 | June | 49 | 35 | 12 | 2 | 24 | 0 | 16 | 16 | 3 | 0 | 0 | 20 | 0 | 11 | 0 | 0 | 1 | 0 | 5 | 0 | 2 | 0 | 0 | 0 | 0 | 51.02% | 10.2% | SR | 2021/22 | July | 2022/23 | January |  | 1.591 | 0.6 |  |  |  |  | 2.191 | 0.7 |  |  | 2.891 | 0.059 | 40 | 0 | 0 | 30 | 20 | 0 | 40 | 30 | 20 | 90
P40182 | Cupar Road Phase 2 | Bonnybank | Levenmouth | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2019/20 | February | 14 | 8 | 6 | 0 | 8 |  | 8 |  |  |  |  | 6 |  | 4 |  | 2 |  |  | 0 | [6 empty] | 42.86% | 0% | SR | 2019/20 | March | 2021/22 | July |  | 1.119 | [5 empty] | 1.119 |  |  |  | 1.119 | 0.079929 | 50 | 25 | 30 | 70 | 0 | 0 | 75 | 100 | 0 | 175
TBC | Former Denbeath Church | Buckhaven | Levenmouth | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2022/23 | April | 9 | 9 |  |  | 9 | 1 | 2 | 6 |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2022/23 | April | 2022/23 | March |  |  | 0.702 |  |  |  |  | 0.702 |  |  |  | 0.702 | 0.078 | 40 | 25 | 0 | 30 | 0 | 0 | 65 | 30 | 0 | 95
TBC | Former Greenmount Hotel | Burntisland | Kirkcaldy | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2025/26 | April | 0 | 15 | 8 | 0 | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2025/26 | April | 2026/27 | June | [5 empty] | 1.794 |  | 1.794 |  |  |  | 1.794 | 0.078 | 50 | 45 | 0 | 30 | 0 | 0 | 95 | 30 | 0 | 125 | Units to be delivered - 23
TBC | Ged Mill Close | Burntisland | Kirkcaldy | Kirkcaldy, Glenrothes & Central | KHA | KI | 2020/21 | March | 6 | 6 | 0 | 0 | 6 |  | 6 |  |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | MMR 30 | 2020/21 | March | 2021/22 | March |  | 0.288 | [5 empty] | 0.288 |  |  |  | 0.288 | 0.048 | 50 | 45 | 0 | 30 | 0 | 0 | 95 | 30 | 0 | 125
P40188 | Grange Road | Burntisland | Kirkcaldy | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2024/25 | August | 3 | 2 | 1 | 0 | 1 |  | 1 |  |  |  |  | 2 |  | 2 |  |  |  |  | 0 | [6 empty] | 33.33% | 0% | SR | 2024/25 | August | 2024/25 | March |  |  |  |  | 0.228 |  |  | 0.228 |  |  |  | 0.228 | 0.076 | 50 | 45 | 0 | 10 | 0 | 0 | 95 | 10 | 0 | 105
P41482 | Conscience Bridge | Cairneyhill | West Fife Villages | Dunfermline & West | KHA | KHA | 2023/24 | April | 25 | 16 | 9 | 0 | 16 |  | 12 | 4 |  |  |  | 9 |  | 7 | 2 | 0 |  |  | 0 |  | 0 |  |  |  |  | 36% | 0% | SR | 2023/24 | April | 2024/25 | April |  |  |  | 1.88 |  |  |  | 1.88 |  |  |  | 1.88 | 0.0752 | 40 | 45 | 10 | 30 | 0 | 0 | 85 | 40 | 0 | 125
36226 | Balgonie Grove (Jamphlars Ph1) | Cardenden | Kirkcaldy | Kirkcaldy, Glenrothes & Central | KHA | OVHA | 2019/20 | March | 59 | 41 | 15 | 3 | 41 |  | 19 | 12 | 10 |  |  | 15 |  | 10 |  |  | 5 |  | 3 |  | 2 | 1 |  |  |  | 30.51% | 5.085% | SR | 2020/21 | December | 2021/22 | March | 2 | 2.852 | [5 empty] | 4.852 |  |  |  | 4.852 | 0.082237 | 50 | 45 | 0 | 70 | 0 | 0 | 95 | 70 | 0 | 165
P41451 | Woodend Road | Cardenden | Kirkcaldy | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2020/21 | February | 45 | 35 | 10 | 0 | 35 |  | 24 | 11 |  |  |  | 10 |  | 10 |  |  |  |  | 0 | [6 empty] | 22.22% | 0% | SR | 2020/21 | March | 2022/23 | July | 1 | 2.51 | [5 empty] | 3.51 |  |  |  | 3.51 | 0.078 | 50 | 45 | 30 | 70 | 0 | 0 | 95 | 100 | 0 | 195
T34135 | Main Street | Carnock | West Fife Villages | Dunfermline & West | KHA | KHA | 2023/24 | April | 30 | 19 | 10 | 1 | 19 |  | 14 | 5 |  |  |  | 10 |  | 9 | 0 | 1 |  |  | 1 |  | 1 |  |  |  |  | 36.67% | 3.333% | SR | 2023/24 | April | 2024/25 | March |  |  |  | 2 | 0.16 |  |  | 2.16 |  |  |  | 2.16 | 0.072 | 40 | 0 | 50 | 30 | 0 | 0 | 40 | 80 | 0 | 120
P43210 | Kinglassie Road | Cluny | Kirkcaldy | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2024/25 | January | 20 | 13 | 7 | 0 | 11 |  | 8 | 3 |  |  |  | 9 |  | 7 | 2 |  |  |  | 0 | [6 empty] | 35% | 0% | SR | 2024/25 | January | 2025/26 | March |  |  |  |  | 0.52 | 1 |  | 1.52 |  |  |  | 1.52 | 0.076 | 50 | 45 | 0 | 30 | 0 | 0 | 95 | 30 | 0 | 125
P43400 | Millburn Avenue | Coaltown of Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2024/25 | July | 44 | 27 | 15 | 2 | 40 |  | 17 | 6 |  |  |  | 3 |  | 13 | 2 | 2 |  |  | 1 |  | 2 | 2 |  |  |  | 38.64% | 2.273% | SR | 2024/25 | July | 2025/26 | May |  |  |  |  | 2 | 1.334 |  | 3.334 |  |  |  | 3.334 | 0.075773 | 50 | 45 | 0 | 30 | 0 | 0 | 95 | 30 | 0 | 125
T36573 | Main Street | Colinsburgh | Largo & East Neuk | St Andrews & North East | KHA | KHA | 2023/24 | May | 12 | 4 | 8 | 0 | 4 |  | 4 |  |  |  |  | 8 |  | 8 |  |  |  |  | 0 | [6 empty] | 66.67% | 0% | SR | 2023/24 | May | 2023/24 | March |  |  |  | 0.96 |  |  |  | 0.96 |  |  |  | 0.96 | 0.08 | 30 | 30 | 0 | 10 | 0 | 0 | 60 | 10 | 0 | 70
T36574 | Main Street | Colinsburgh | Largo & East Neuk | St Andrews & North East | KHA | KI | 2023/24 | May | 4 | 2 | 2 | 0 | 2 |  | 2 |  |  |  |  | 2 |  | 2 |  |  |  |  | 0 | [6 empty] | 50% | 0% | MMR 30 | 2023/24 | May | 2023/24 | March |  |  |  | 0.188 |  |  |  | 0.188 |  |  |  | 0.188 | 0.047 | 30 | 30 | 0 | 10 | 0 | 0 | 60 | 10 | 0 | 70
T36507 | High Street | Cowdenbeath | Cowdenbeath | Dunfermline & West | KHA | OVHA | 2021/22 | September | 29 | 29 |  |  | 29 | 12 | 4 | 13 |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2021/22 | September | 2022/23 | September |  | 0.6 | 1.662 |  |  |  |  | 2.262 |  |  |  | 2.262 | 0.078 | 40 | 25 | 0 | 70 | 0 | 0 | 65 | 70 | 0 | 135
P44406 | Natal Place | Cowdenbeath | Cowdenbeath | Dunfermline & West | KHA | KHA | 2020/21 | September | 2 | 1 | 1 | 0 | 0 | [6 empty] | 2 | [6 empty] | 0 | [6 empty] | 50% | 0% | SR | 2020/21 | September | 2021/22 | April | 0.157 | [6 empty] | 0.157 |  |  |  | 0.157 | 0.0785 | 40 | 25 | 80 | 70 | 20 | 20 | 65 | 150 | 40 | 255
P41381 | Valley House, Hill Street | Cowdenbeath | Cowdenbeath | Dunfermline & West | FC | FC | 2021/22 | October | 22 | 18 | 4 | 0 | 18 | 0 | 0 | 14 | 4 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.18% | 0% | SR | 2021/22 | November | 2022/23 | October | 0.055 | 0.5 | 0.243 |  |  |  |  | 0.798 | 0.5 |  |  | 1.298 | 0.059 | 40 | 25 | 50 | 70 | 0 | 0 | 65 | 120 | 0 | 185
P44074 | Ordnance Road | Crombie | West Fife Villages | Dunfermline & West | FC PSD | FC | 2021/22 | April | 19 | 14 | 5 | 0 | 14 | 0 | 4 | 8 | 2 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.32% | 0% | SR | 2021/22 | April | 2021/22 | March |  | 0.621 | [5 empty] | 0.621 | 0.5 |  |  | 1.121 | 0.059 | 40 | 0 | 30 | 70 | 0 | 0 | 40 | 100 | 0 | 140
P41484 | Pitconochie Farm | Crossford | Dunfermline & Coast | Dunfermline & West | KHA | KHA | 2021/22 | March | 48 | 28 | 18 | 1 | 28 |  | 22 | 6 |  |  |  | 18 |  | 13 | 3 | 2 |  |  | 2 |  | 1 | 1 |  |  |  | 39.58% | 4.167% | SR | 2021/22 | March | 2022/23 | March |  | 0.3 | 2 | 1.444 |  |  |  | 3.744 |  |  |  | 3.744 | 0.078 | 40 | 0 | 40 | 70 | 0 | 0 | 40 | 110 | 0 | 150
P41457 | Manse Road (CRO002) | Crossgates | Cowdenbeath | Dunfermline & West | FC PSD | FC | 2025/26 | June | 0 | 35 | 13 | 2 | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2025/26 | June | 2026/27 | November | [5 empty] | 1.45 | 1.4918 | 2.9418 |  | 0.008 |  | 2.9498 | 0.061455 | 40 | 25 | 0 | 10 | 0 | 0 | 65 | 10 | 0 | 75
P41314 | Inchgall Avenue MS | Crosshill | Cowdenbeath | Dunfermline & West | FC | FC | 2022/23 | April | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 100% | SR | 2022/23 | April | 2022/23 | November |  |  | 0.236 |  |  |  |  | 0.236 |  |  |  | 0.236 | 0.059 | 40 | 25 | 50 | 30 | 0 | 0 | 65 | 80 | 0 | 145
P43184 | Carslogie Road (Former Police Station) | Cupar | Cupar & HOF | Cupar & North West | FC | FC | 2021/22 | October | 13 | 9 | 3 | 1 | 9 | 0 | 4 | 4 | 1 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 30.77% | 7.692% | SR | 2021/22 | November | 2022/23 | October | 0.3 | 0.467 | [5 empty] | 0.767 |  |  |  | 0.767 | 0.059 | 20 | 15 | 50 | 30 | 0 | 0 | 35 | 80 | 0 | 115
P41491 | Cupar North (Phase1A) | Cupar | Cupar & HOF | Cupar & North West | KHA | KHA | 2025/26 | April | 0 | 17 | 8 | 0 | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2025/26 | April | 2026/27 | March | [5 empty] | 2 |  | 2 |  |  |  | 2 | 0.11765 | 20 | 15 | 10 | 30 | 0 | 0 | 35 | 40 | 0 | 75 | Units to be delivered - 25
P41492 | Cupar North (Phase1B) | Cupar | Cupar & HOF | Cupar & North West | KHA | KI | 2025/26 | April | 0 | 6 | 0 | 0 | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | MMR 30 | 2025/26 | April | 2026/27 | March | [5 empty] | 0.294 |  | 0.294 |  |  |  | 0.294 | 0.049 | 20 | 15 | 10 | 30 | 0 | 0 | 35 | 40 | 0 | 75 | Units to be delivered - 6
P44702 | Bank Street (Former Dalgairn Centre) (New Care Village) | Cupar | Cupar & HOF | Cupar & North West | FC | FC | 2022/23 | May | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | 2022/23 | May | 2023/24 | December |  |  | 0.467 | 0.448 |  |  |  | 0.915 |  | 0.033 |  | 0.948 | 0.079 | 20 | 15 | 50 | 30 | 20 | 20 | 35 | 80 | 40 | 155
P41477 | Gilliesfaulds (Phase 2 - MMR) | Cupar | Cupar & HOF | Cupar & North West | KHA | KI | 2023/24 | June | 12 | 6 | 6 | 0 | 12 |  | 6 | 6 |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 50% | 0% | MMR 30 | 2023/24 | June | 2024/25 | February |  |  |  | 0.564 |  |  |  | 0.564 |  |  |  | 0.564 | 0.047 | 20 | 15 | 10 | 30 | 0 | 0 | 35 | 40 | 0 | 75
P41479 | Gilliesfaulds (Phase 2 - SR) | Cupar | Cupar & HOF | Cupar & North West | KHA | KHA | 2023/24 | June | 38 | 25 | 13 | 0 | 25 |  | 19 | 6 |  |  |  | 13 |  | 8 | 3 | 2 |  |  | 0 | [6 empty] | 34.21% | 0% | SR | 2023/24 | June | 2024/25 | February |  |  |  | 3 |  |  |  | 3 |  |  |  | 3 | 0.078947 | 20 | 15 | 10 | 30 | 0 | 0 | 35 | 40 | 0 | 75
P41467 | Gilliesfaulds Phase 1 (SR) | Cupar | Cupar & HOF | Cupar & North West | KHA | KHA | 2021/22 | April | 13 | 8 | 4 | 0 | 8 |  | 8 |  |  |  |  | 4 |  | 4 |  |  |  |  | 1 |  | 1 |  |  |  |  | 30.77% | 7.692% | SR | 2021/22 | April | 2021/22 | March |  | 1.014 | [5 empty] | 1.014 |  |  |  | 1.014 | 0.078 | 20 | 15 | 40 | 70 | 0 | 0 | 35 | 110 | 0 | 145
TBC | Inner Court | Cupar | Cupar & HOF | Cupar & North West | KHA | KI | 2021/22 | April | 23 | 23 | 0 | 0 | 23 | 2 | 21 |  |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | MMR 30 | 2021/22 | April | 2022/23 | November |  | 1.152 | [5 empty] | 1.152 |  | 0.013 |  | 1.165 | 0.050652 | 20 | 15 | 0 | 70 | 0 | 0 | 35 | 70 | 0 | 105
P41458 | Eden Park (Former Care Home) | Cupar | Cupar & HOF | Cupar & North West | FC | FC | 2023/24 | February | 10 | 7 | 2 | 1 | 7 | 0 | 3 | 3 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 30% | 10% | SR | 2023/24 | February | 2024/25 | January |  |  |  |  | 0.59 |  |  | 0.59 |  |  |  | 0.59 | 0.059 | 20 | 15 | 50 | 30 | 0 | 0 | 35 | 80 | 0 | 115
P41461 | Aberdour Road (Former Pitcorthie PS) (EC Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West | FC | FC | 2021/22 | October | 18 | 0 | 16 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 16 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 100% | 11.11% | SR | 2021/22 | November | 2022/23 | October | 0.455 | 0.607 | [5 empty] | 1.062 |  |  |  | 1.062 | 0.059 | 40 | 45 | 50 | 30 | 0 | 0 | 85 | 80 | 0 | 165
P43209 | Bellyeoman Road | Dunfermline | Dunfermline & Coast | Dunfermline & West | KHA | KHA | 2024/25 | October | 22 | 15 | 7 | 0 | 15 |  | 11 | 4 |  |  |  | 7 |  | 6 |  | 1 |  |  | 0 | [6 empty] | 31.82% | 0% | SR | 2024/25 | October | 2025/26 | October |  |  |  |  | 1.672 |  |  | 1.672 |  |  |  | 1.672 | 0.076 | 40 | 45 | 10 | 10 | 0 | 0 | 85 | 20 | 0 | 105
P41465 | Blacklaw Road Phase 2 (EC Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West | FC | FC | 2022/23 | April | 40 | 28 | 10 | 2 | 20 | 0 | 13 | 12 | 3 | 0 | 0 | 10 | 0 | 9 | 0 | 0 | 1 | 0 | 10 | 0 | 1 | 1 | 0 | 0 | 0 | 50% | 25% | SR | 2022/23 | April | 2023/24 | March |  |  | 1 | 1.36 |  |  |  | 2.36 |  |  |  | 2.36 | 0.059 | 40 | 45 | 50 | 30 | 0 | 0 | 85 | 80 | 0 | 165
P41503 | Broomhall (Phase 1) | Dunfermline | Dunfermline & Coast | Dunfermline & West | KHA | KI | 2022/23 | April | 30 | 19 | 11 | 0 | 19 |  | 14 | 5 |  |  |  | 11 |  | 10 |  | 1 |  |  | 0 | [6 empty] | 36.67% | 0% | MMR 30 | 2022/23 | April | 2024/25 | May |  |  | 1.35 |  |  |  |  | 1.35 |  |  |  | 1.35 | 0.045 | 40 | 45 | 10 | 30 | 20 | 20 | 85 | 40 | 40 | 165
P41504 | Broomhall (Phase 2) | Dunfermline | Dunfermline & Coast | Dunfermline & West | KHA | KHA | 2022/23 | April | 40 | 27 | 13 | 0 | 27 |  | 21 | 6 |  |  |  | 13 |  | 11 |  | 2 |  |  | 0 | [6 empty] | 32.5% | 0% | SR | 2022/23 | April | 2024/25 | May |  |  | 2.34 | 0.7 |  |  |  | 3.04 |  |  |  | 3.04 | 0.076 | 40 | 45 | 10 | 30 | 20 | 20 | 85 | 40 | 40 | 165
P41505 | Broomhall SLA, Future Phases | Dunfermline | Dunfermline & Coast | Dunfermline & West | KHA | KHA | 2025/26 | June | 0 | 33 | 16 | 2 | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2025/26 | June | 2026/27 | March | [5 empty] | 3.9 |  | 3.9 |  |  |  | 3.9 | 0.078 | 40 | 45 | 10 | 30 | 0 | 0 | 85 | 40 | 0 | 125 | Units to be delivered - 50
T36505 | Freescale Dunlin (Bellway) - Phase 2 | Dunfermline | Dunfermline & Coast | Dunfermline & West | KHA | KHA | 2024/25 | July | 27 | 19 | 8 | 0 | 17 |  | 11 | 6 |  |  |  | 10 |  | 5 | 4 | 1 |  |  | 0 | [6 empty] | 29.63% | 0% | SR | 2024/25 | July | 2025/26 | July |  |  |  |  | 2.025 |  |  | 2.025 |  |  |  | 2.025 | 0.075 | 40 | 45 | 10 | 30 | 0 | 0 | 85 | 40 | 0 | 125
T36506 | Freescale Dunlin (Persimmon) - Phase 1 | Dunfermline | Dunfermline & Coast | Dunfermline & West | KHA | KHA | 2022/23 | July | 27 | 19 | 7 | 1 | 19 |  | 13 | 6 |  |  |  | 7 |  | 7 |  | 0 |  |  | 1 |  | 1 |  |  |  |  | 29.63% | 3.704% | SR | 2022/23 | August | 2023/24 | November |  |  | 1.252 | 0.85 |  |  |  | 2.102 |  |  |  | 2.102 | 0.077852 | 40 | 45 | 10 | 30 | 0 | 0 | 85 | 40 | 0 | 125
P43286 | Halbeath SDA | Dunfermline | Dunfermline & Coast | Dunfermline & West | FC PSD | FC | 2022/23 | April | 0 | 60 | 21 | 4 | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2022/23 | April | 2026/27 | June |  |  | 1.6 | 1.8 | 1.615 |  |  | 5.015 |  |  |  | 5.015 | 0.059 | 40 | 45 | 0 | 70 | 0 | 20 | 85 | 70 | 20 | 175
P41489 | Meadowlands North | Dunfermline | Dunfermline & Coast | Dunfermline & West | KHA | KHA | 2020/21 | January | 29 | 29 | 0 | 0 | 29 |  | 25 | 4 |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2020/21 | March | 2021/22 | April | 0.6 | 1.65 | [5 empty] | 2.25 |  |  |  | 2.25 | 0.077586 | 40 | 45 | 30 | 70 | 0 | 0 | 85 | 100 | 0 | 185
P43414 | Milesmark (DUN033) | Dunfermline | Dunfermline & Coast | Dunfermline & West | FC PSD | FC | 2024/25 | April | 20 | 14 | 5 | 1 | 12 | 0 | 6 | 5 | 1 | 0 | 0 | 8 | 0 | 5 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40% | 0% | SR | 2024/25 | April | 2024/25 | March |  |  |  |  | 1.18 |  |  | 1.18 |  |  |  | 1.18 | 0.059 | 40 | 45 | 0 | 10 | 0 | 0 | 85 | 10 | 0 | 95
P41462 | North Fod Phase 2 | Dunfermline | Dunfermline & Coast | Dunfermline & West | FC | FC | 2022/23 | April | 49 | 35 | 12 | 2 | 35 | 0 | 16 | 16 | 3 | 0 | 0 | 12 | 0 | 11 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 28.57% | 4.082% | SR | 2022/23 | May | 2024/25 | April |  |  | 1 | 1.891 |  |  |  | 2.891 |  |  |  | 2.891 | 0.059 | 40 | 45 | 50 | 30 | 0 | 0 | 85 | 80 | 0 | 165
P43182 | Pilmuir Street (Block 1) | Dunfermline | Dunfermline & Coast | Dunfermline & West | KI | KI | 2019/20 | August | 33 | 33 | 0 | 0 | 33 |  | 33 |  |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | MMR 30 | 2019/20 | September | 2021/22 | September | 1.626 | [6 empty] | 1.626 |  |  |  | 1.626 | 0.049273 | 40 | 45 | 90 | 70 | 0 | 0 | 85 | 160 | 0 | 245
P43208 | Pilmuir Street (Block 2) | Dunfermline | Dunfermline & Coast | Dunfermline & West | KI | KI | 2019/20 | August | 33 | 33 | 0 | 0 | 33 |  | 33 |  |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | MMR 30 | 2019/20 | September | 2021/22 | September | 1.626 | [6 empty] | 1.626 |  |  |  | 1.626 | 0.049273 | 40 | 45 | 90 | 70 | 0 | 0 | 85 | 160 | 0 | 245
P41459 | Rumblingwell (Former Milesmark Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West | FC PSD | FC | 2024/25 | April | 12 | 8 | 3 | 1 | 8 | 0 | 4 | 3 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 33.33% | 16.67% | SR | 2024/25 | April | 2024/25 | March |  |  |  |  | 0.708 |  |  | 0.708 |  |  |  | 0.708 | 0.059 | 40 | 45 | 0 | 10 | 0 | 0 | 85 | 10 | 0 | 95
P43407 | South Castle Drive | Dunfermline | Dunfermline & Coast | Dunfermline & West | KI | KI | 2022/23 | August | 18 | 12 | 6 | 0 | 12 |  | 11 | 1 |  |  |  | 6 |  | 6 |  |  |  |  | 0 | [6 empty] | 33.33% | 0% | MMR 30 | 2022/23 | September | 2023/24 | October |  |  | 0.828 |  |  |  |  | 0.828 |  |  |  | 0.828 | 0.046 | 40 | 45 | 0 | 30 | 0 | 0 | 85 | 30 | 0 | 115
P41463 | Townhill Road (DUN038) Phase 1 | Dunfermline | Dunfermline & Coast | Dunfermline & West | FC PSD | FC | 2022/23 | November | 23 | 15 | 5 | 3 | 15 | 0 | 5 | 5 | 5 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 34.78% | 13.04% | SR | 2022/23 | December | 2023/24 | December |  |  | 0.4 | 0.957 |  |  |  | 1.357 |  |  |  | 1.357 | 0.059 | 40 | 45 | 10 | 10 | 0 | 0 | 85 | 20 | 0 | 105
P43377 | Woodmill Street MS | Dunfermline | Dunfermline & Coast | Dunfermline & West | FC | FC | 2022/23 | May | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 100% | 100% | SR | 2022/23 | June | 2022/23 | December |  |  | 0.354 |  |  |  |  | 0.354 |  |  |  | 0.354 | 0.059 | 40 | 45 | 50 | 30 | 0 | 0 | 85 | 80 | 0 | 165
P43199 | Borelands Road | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2021/22 | April | 34 | 24 | 8 | 2 | 24 | 0 | 11 | 11 | 2 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 29.41% | 5.882% | SR | 2021/22 | April | 2023/24 | March |  | 1 | 0.406 |  |  |  |  | 1.406 | 0.6 |  |  | 2.006 | 0.059 | 50 | 45 | 0 | 30 | 0 | 0 | 95 | 30 | 0 | 125
P41450 | Wadeslea | Elie | Largo & East Neuk | St Andrews & North East | KHA | KHA | 2024/25 | July | 12 | 6 | 6 | 0 | 6 |  | 6 |  |  |  |  | 6 |  | 6 |  |  |  |  | 0 | [6 empty] | 50% | 0% | SR | 2024/25 | July | 2025/26 | May |  |  |  |  | 0.912 |  |  | 0.912 |  |  |  | 0.912 | 0.076 | 30 | 30 | 0 | 30 | 0 | 0 | 60 | 30 | 0 | 90
P44703 | St Johns Works | Falkland | Glenrothes | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2021/22 | June | 30 | 21 | 5 | 4 | 21 |  | 3 | 14 | 4 |  |  | 5 |  | 4 |  |  | 1 |  | 4 |  | 3 | 1 |  |  |  | 30% | 13.33% | SR | 2021/22 | July | 2022/23 | June |  | 0.9 | 0.87 |  |  |  |  | 1.77 |  |  |  | 1.77 | 0.059 | 50 | 15 | 0 | 10 | 0 | 0 | 65 | 10 | 0 | 75
P41389 | Open Market Transactions 21/22 Phase 1 | Fife | Fife |  | FC | FC | 2021/22 | May | 25 | 18 | 6 | 1 | 25 | 0 | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | 2021/22 | May | 2021/22 | March |  | 1 | [5 empty] | 1 |  |  |  | 1 | 0.04 | 0 | 0 | 0 | 70 | 0 | 20 | 0 | 70 | 20 | 90
P44704 | Open Market Transactions 21/22 Phase 2 | Fife | Fife |  | FC | FC | 2021/22 | December | 25 | 18 | 6 | 1 | 25 | 0 | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | 2021/22 | December | 2021/22 | March |  | 1 | [5 empty] | 1 |  |  |  | 1 | 0.04 | 0 | 0 | 0 | 70 | 0 | 20 | 0 | 70 | 20 | 90
P41390 | Open Market Transactions 22/23 | Fife | Fife |  | FC | FC | 2022/23 | December | 50 | 50 | 0 | 0 | 50 | 0 | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | 2022/23 | December | 2022/23 | March |  |  | 2 |  |  |  |  | 2 |  |  |  | 2 | 0.04 | 0 | 0 | 0 | 70 | 0 | 20 | 0 | 70 | 20 | 90
P41391 | Open Market Transactions 23/24 | Fife | Fife |  | FC | FC | 2023/24 | December | 50 | 50 | 0 | 0 | 50 | 0 | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | 2023/24 | December | 2023/24 | March |  |  |  | 2 |  |  |  | 2 |  |  |  | 2 | 0.04 | 0 | 0 | 0 | 70 | 0 | 20 | 0 | 70 | 20 | 90
P43376 | Open Market Transactions 24/25 | Fife | Fife |  | FC | FC | 2024/25 | December | 50 | 50 | 0 | 0 | 50 | 0 | 20 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | 2024/25 | December | 2024/25 | March |  |  |  |  | 2 |  |  | 2 |  |  |  | 2 | 0.04 | 0 | 0 | 0 | 70 | 0 | 20 | 0 | 70 | 20 | 90
P44705 | Open Market Transactions 25/26 | Fife | Fife |  | FC | FC | 2025/26 | December | 50 |  |  |  | 50 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2025/26 | December | 2025/26 | March | [5 empty] | 2 |  | 2 |  |  |  | 2 | 0.04 | 0 | 0 | 0 | 70 | 0 | 20 | 0 | 70 | 20 | 90
P40353 | Balgove Road | Gauldry | Tay Coast | St Andrews & North East | KHA | KHA | 2020/21 | March | 30 | 20 | 10 |  | 20 |  | 14 | 6 |  |  |  | 10 |  | 10 |  |  |  |  | 0 | [6 empty] | 33.33% | 0% | SR | 2020/21 | March | 2022/23 | April | 1 | 1.34 | [5 empty] | 2.34 |  |  |  | 2.34 | 0.078 | 10 | 10 | 0 | 70 | 0 | 0 | 20 | 70 | 0 | 90
P40203 | Detroit Road | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | FC | FC | 2023/24 | March | 45 | 32 | 11 | 2 | 28 | 0 | 12 | 13 | 3 | 0 | 0 | 13 | 0 | 9 | 2 | 0 | 2 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 28.89% | 8.889% | SR | 2024/25 | April | 2025/26 | March |  |  |  |  | 1.655 | 1 |  | 2.655 |  |  |  | 2.655 | 0.059 | 50 | 45 | 0 | 10 | 0 | 0 | 95 | 10 | 0 | 105
P41471 | Glenwood | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | FC | FC | 2024/25 | April | 25 | 18 | 6 | 1 | 9 | 0 | 3 | 3 | 3 | 0 | 0 | 10 | 0 | 7 | 2 | 1 | 0 | 0 | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 64% | 24% | SR | 2024/25 | April | 2025/26 | September |  |  |  |  | 1 | 0.475 |  | 1.475 |  |  |  | 1.475 | 0.059 | 50 | 45 | 50 | 10 | 0 | 20 | 95 | 60 | 20 | 175
TBC | Napier Road, (Former Police Station) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2025/26 | April | 0 | 24 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2025/26 | April | 2026/27 | March | [5 empty] | 1.872 |  | 1.872 |  |  |  | 1.872 | 0.078 | 50 | 45 | 10 | 10 | 0 | 0 | 95 | 20 | 0 | 115 | Units to be delivered - 24
P43856 | Queensgate, Former Tullis Russell Mill | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2020/21 | October | 85 | 60 | 21 | 4 | 60 |  | 22 | 27 | 11 |  |  | 21 |  | 6 | 8 | 2 | 5 |  | 4 |  | 2 | 2 |  |  |  | 29.41% | 4.706% | SR | 2020/21 | November | 2022/23 | January | 4 | 2 | 0.579 |  |  |  |  | 6.579 |  |  |  | 6.579 | 0.0774 | 50 | 45 | 60 | 70 | 0 | 0 | 95 | 130 | 0 | 225
P43855 | Queensgate, Former Tullis Russell Mill Phase 2 | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | KHA | KI | 2021/22 | April | 20 | 18 | 2 |  | 18 |  | 10 | 8 |  |  |  | 2 |  | 2 |  |  |  |  | 0 | [6 empty] | 10% | 0% | MMR 30 | 2021/22 | April | 2022/23 | April | 0.2 | 0.76 | [5 empty] | 0.96 |  |  |  | 0.96 | 0.048 | 50 | 45 | 0 | 70 | 0 | 0 | 95 | 70 | 0 | 165
P41392 | Viewfield | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | FC | FC | 2022/23 | April | 49 | 35 | 12 | 2 | 35 | 0 | 16 | 16 | 3 | 0 | 0 | 12 | 0 | 11 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 28.57% | 4.082% | SR | 2022/23 | April | 2024/25 | March |  |  | 0.718 | 0.717 | 0.717 |  |  | 2.152 | 0.7 | 0.039 |  | 2.891 | 0.059 | 50 | 45 | 50 | 30 | 0 | 0 | 95 | 80 | 0 | 175
P41364 | Westwood Park | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2021/22 | April | 34 | 24 | 8 | 2 | 24 | 0 | 11 | 11 | 2 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 29.41% | 5.882% | SR | 2021/22 | April | 2022/23 | October |  | 0.9 | 0.506 |  |  |  |  | 1.406 | 0.6 |  |  | 2.006 | 0.059 | 50 | 45 | 40 | 30 | 0 | 0 | 95 | 70 | 0 | 165
P44706 | Westwood Phase 2 | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2021/22 | November | 60 | 42 | 15 | 3 | 42 | 0 | 19 | 19 | 4 | 0 | 0 | 15 | 0 | 14 | 0 | 0 | 1 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 30% | 5% | SR | 2021/22 | December | 2024/25 | November |  | 0.4 | 1.1 | 1.34 |  |  |  | 2.84 | 0.7 |  |  | 3.54 | 0.059 | 50 | 45 | 0 | 30 | 0 | 0 | 95 | 30 | 0 | 125
P41365 | Seggie Farm Phase 2 | Guardbridge | St Andrews | St Andrews & North East | FC | FC | 2020/21 | July | 33 | 19 | 8 | 6 | 19 | 0 | 2 | 9 | 8 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 6 | 0 | 4 | 1 | 1 | 0 | 0 | 42.42% | 18.18% | SR | 2020/21 | July | 2022/23 | September | 1 | 0.455 | [5 empty] | 1.455 | 0.4 | 0.0924 |  | 1.9474 | 0.059012 | 30 | 50 | 90 | 70 | 0 | 0 | 80 | 160 | 0 | 240
P41473 | Seggie Farm Phase 3 | Guardbridge | St Andrews | St Andrews & North East | FC | FC | 2021/22 | November | 35 | 27 | 8 | 0 | 27 | 0 | 15 | 12 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.86% | 0% | SR | 2021/22 | January | 2023/24 | July |  | 0.5 | 1.265 | 0.3 |  |  |  | 2.065 |  |  |  | 2.065 | 0.059 | 30 | 50 | 90 | 70 | 0 | 0 | 80 | 160 | 0 | 240
T36451 | Toll Road Phase 2A | Guardbridge | St Andrews | St Andrews & North East | KHA | KHA | 2020/21 | January | 20 | 13 | 6 | 1 | 13 |  | 5 | 8 |  |  |  | 6 |  | 4 | 1 | 1 |  |  | 1 |  | 1 |  |  |  |  | 35% | 5% | SR | 2020/21 | January | 2021/22 | January | 0.826 | 0.734 | [5 empty] | 1.56 |  |  |  | 1.56 | 0.078 | 30 | 50 | 50 | 30 | 20 | 20 | 80 | 80 | 40 | 200
T36452 | Toll Road Phase 2B | Guardbridge | St Andrews | St Andrews & North East | KHA | KHA | 2020/21 | January | 10 | 10 |  |  | 10 |  | 10 |  |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | MMR 30 | 2020/21 | January | 2021/22 | January | 0.495 | [6 empty] | 0.495 |  |  |  | 0.495 | 0.0495 | 30 | 50 | 50 | 30 | 0 | 0 | 80 | 80 | 0 | 160
P41315 | Chapel Place MS | High Valleyfield | West Fife Villages | Dunfermline & West | FC | FC | 2022/23 | May | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 100% | SR | 2022/23 | June | 2022/23 | December |  |  | 0.1725 |  |  |  |  | 0.1725 |  | 0.0045 |  | 0.177 | 0.059 | 40 | 0 | 50 | 30 | 0 | 0 | 40 | 80 | 0 | 120
P41400 | Daly Gardens | High Valleyfield | West Fife Villages | Dunfermline & West | FC | FC | 2022/23 | May | 20 | 14 | 5 | 1 | 14 | 0 | 7 | 6 | 1 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 30% | 5% | SR | 2022/23 | May | 2023/24 | May |  |  | 0.59 | 0.59 |  |  |  | 1.18 |  |  |  | 1.18 | 0.059 | 40 | 0 | 0 | 30 | 0 | 0 | 40 | 30 | 0 | 70
T36239 | Echobank | Inverkeithing | Dunfermline & Coast | Dunfermline & West | KHA | KI | 2024/25 | April | 12 | 8 | 4 | 0 | 8 |  | 6 | 2 |  |  |  | 4 |  | 4 |  |  |  |  | 0 | [6 empty] | 33.33% | 0% | MMR 30 | 2024/25 | April | 2024/25 | March |  |  |  |  | 0.564 |  |  | 0.564 |  |  |  | 0.564 | 0.047 | 40 | 45 | 0 | 10 | 0 | 0 | 85 | 10 | 0 | 95
T36504 | Fraser Avenue Phase 2 | Inverkeithing | Dunfermline & Coast | Dunfermline & West | KHA | KHA | 2018/19 | March | 61 | 42 | 16 | 3 | 42 |  | 16 | 15 | 7 | 4 |  | 16 |  | 16 |  |  |  |  | 3 |  | 2 | 1 |  |  |  | 31.15% | 4.918% | SR | 2019/20 | March | 2022/23 | June | 3.6 | 1.554 | [5 empty] | 5.154 |  |  |  | 5.154 | 0.084492 | 40 | 45 | 80 | 70 | 0 | 0 | 85 | 150 | 0 | 235
P41447 | Fraser Avenue Phase 3 | Inverkeithing | Dunfermline & Coast | Dunfermline & West | KHA | KHA | 2022/23 | May | 47 | 30 | 15 | 2 | 30 |  | 21 | 9 |  |  |  | 15 |  | 13 |  | 2 |  |  | 2 |  | 2 |  |  |  |  | 36.17% | 4.255% | SR | 2022/23 | May | 2023/24 | March |  |  | 1.8 | 2.072 |  |  |  | 3.872 | 0.15 |  |  | 4.022 | 0.085574 | 40 | 45 | 0 | 70 | 0 | 0 | 85 | 70 | 0 | 155
P41448 | Fraser Avenue Phase 4 | Inverkeithing | Dunfermline & Coast | Dunfermline & West | KHA | KHA | 2024/25 | March | 41 | 23 | 16 | 2 | 23 |  | 19 | 4 |  |  |  | 17 |  | 10 | 3 | 4 |  |  | 1 |  | 1 |  |  |  |  | 43.9% | 2.439% | SR | 2024/25 | March | 2025/26 | October |  |  |  |  | 0.3 | 2.34 |  | 2.64 |  |  |  | 2.64 | 0.06439 | 40 | 45 | 0 | 30 | 0 | 0 | 85 | 30 | 0 | 115
P44511 | Prestonhill Quarry | Inverkeithing | Dunfermline & Coast | Dunfermline & West | KHA | KHA | 2025/26 | October | 0 | 24 | 11 |  | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2025/26 | October | 2026/27 | March | [5 empty] | 1 | 1.73 | 2.73 |  |  |  | 2.73 | 0.078 | 40 | 45 | 10 | 30 | 0 | 0 | 85 | 40 | 0 | 125 | Units to be delivered - 35
P43398 | Black Road | Kelty | Cowdenbeath | Dunfermline & West | KHA | KHA | 2024/25 | April | 30 | 19 | 11 | 0 | 18 |  | 14 | 4 |  |  |  | 12 |  | 11 | 1 |  |  |  | 0 | [6 empty] | 36.67% | 0% | SR | 2024/25 | May | 2025/26 | September |  |  |  |  | 2.28 |  |  | 2.28 |  |  |  | 2.28 | 0.076 | 40 | 25 | 0 | 30 | 0 | 0 | 65 | 30 | 0 | 95
P41480 | Keltyhill Road | Kelty | Cowdenbeath | Dunfermline & West | KHA | KHA | 2025/26 | August | 6 | 3 | 3 | 0 | 3 |  | 3 |  |  |  |  | 3 |  | 3 |  |  |  |  | 0 | [6 empty] | 50% | 0% | SR | 2025/26 | August | 2025/26 | February | [5 empty] | 0.231 |  | 0.231 |  |  |  | 0.231 | 0.0385 | 40 | 25 | 0 | 30 | 0 | 0 | 65 | 30 | 0 | 95
P44716 | Hallfields Gardens | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2021/22 | October | 20 | 14 | 5 | 1 | 13 | 0 | 6 | 6 | 1 | 0 | 0 | 6 | 0 | 5 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 35% | 5% | SR | 2021/22 | October | 2022/23 | September |  | 0.68 | 0.5 |  |  |  |  | 1.18 |  |  |  | 1.18 | 0.059 | 50 | 25 | 0 | 30 | 0 | 0 | 75 | 30 | 0 | 105
P41322 | Langside Crescent Phase 2 | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | FC | FC | 2021/22 | October | 36 | 25 | 9 | 2 | 25 | 0 | 12 | 11 | 2 | 0 | 0 | 9 | 0 | 8 | 0 | 0 | 1 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 30.56% | 5.556% | SR | 2021/22 | November | 2023/24 | April | 0.3 | 0.5 | 0.824 |  |  |  |  | 1.624 | 0.5 |  |  | 2.124 | 0.059 | 50 | 25 | 50 | 70 | 0 | 0 | 75 | 120 | 0 | 195
TBC | Langside Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2025/26 | April | 0 | 24 | 14 | 2 | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2025/26 | April | 2026/27 | March | [5 empty] | 2.5 | 0.62 | 3.12 |  |  |  | 3.12 | 0.078 | 50 | 25 | 0 | 30 | 0 | 0 | 75 | 30 | 0 | 105 | Units to be delivered - 40
P41374 | Upper Forth View Phase 2 | Kincardine | West Fife Villages | Dunfermline & West | FC | FC | 2024/25 | November | 30 | 21 | 7 | 2 | 21 | 0 | 10 | 9 | 2 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 30% | 13.33% | SR | 2024/25 | November | 2025/26 | October |  |  |  |  | 0.77 | 1 |  | 1.77 |  |  |  | 1.77 | 0.059 | 40 | 0 | 0 | 10 | 0 | 0 | 40 | 10 | 0 | 50
P40812 | Upper Forth View, Phase 1 | Kincardine | West Fife Villages | Dunfermline & West | FC | FC | 2023/24 | November | 30 | 21 | 7 | 2 | 21 | 0 | 10 | 9 | 2 | 0 | 0 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 6.667% | SR | 2023/24 | November | 2024/25 | October |  |  |  | 0.77 | 0.95698 |  |  | 1.727 |  | 0.043 |  | 1.77 | 0.058999 | 40 | 0 | 0 | 10 | 0 | 0 | 40 | 10 | 0 | 50
P41375 | Upper Forth View, Phase 3 | Kincardine | West Fife Villages | Dunfermline & West | FC | FC | 2025/26 | November | 0 | 18 | 6 | 1 | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2025/26 | November | 2026/27 | October | [5 empty] | 0.7 | 0.775 | 1.475 |  |  |  | 1.475 | 0.059 | 40 | 0 | 0 | 10 | 0 | 0 | 40 | 10 | 0 | 50
P43401 | Cuddyhouse Road | Kingseat | Dunfermline & Coast | Dunfermline & West | KHA | KHA | 2024/25 | March | 30 | 16 | 13 | 1 | 17 |  | 16 | 1 |  |  |  | 11 |  | 10 | 1 |  |  |  | 2 |  | 1 | 1 |  |  |  | 46.67% | 6.667% | SR | 2024/25 | March | 2025/26 | March |  |  |  |  | 0.28 | 2 |  | 2.28 |  |  |  | 2.28 | 0.076 | 40 | 45 | 0 | 10 | 0 | 0 | 85 | 10 | 0 | 95
P43853 | Main Street | Kingseat | Dunfermline & Coast | Dunfermline & West | FC PSD | FC | 2020/21 | August | 18 | 14 | 4 | 0 | 14 | 0 | 5 | 9 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.22% | 0% | SR | 2020/21 | September | 2021/22 | March | 1.062 | 0 | [5 empty] | 1.062 |  |  |  | 1.062 | 0.059 | 40 | 45 | 80 | 70 | 0 | 0 | 85 | 150 | 0 | 235
T36567 | 251-261 High Street (Former Co-op) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | FC | FC | 2020/21 | November | 39 | 37 | 2 | 0 | 37 | 0 | 37 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.128% | 0% | SR | 2020/21 | December | 2022/23 | June | 0.8 | 1.501 | [5 empty] | 2.301 |  |  |  | 2.301 | 0.059 | 50 | 45 | 50 | 70 | 10 | 20 | 95 | 120 | 30 | 245
T36221 | Glen Albyn Drive, Phase 1 & 2 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | FHG | FHG | 2020/21 | January | 49 | 14 | 5 | 1 | 35 |  | 16 | 16 | 3 |  |  | 12 |  | 11 |  |  | 1 |  | 2 |  | 2 |  |  |  |  | 28.57% | 4.082% | SR | 2021/22 | April | 2022/23 | December | 0.3 | 2 | 1.63 |  |  |  |  | 3.93 |  |  |  | 3.93 | 0.080204 | 50 | 45 | 50 | 30 | 0 | 0 | 95 | 80 | 0 | 175
P41500 | Kingdom Park Phase 1 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | KI | KI | 2019/20 | October | 20 | 20 | 0 | 0 | 20 |  | 18 |  | 2 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | MMR 30 | 2019/20 | January | 2021/22 | September | 0.55 | 0.445 | [5 empty] | 0.995 |  |  |  | 0.995 | 0.04975 | 50 | 45 | 40 | 70 | 0 | 20 | 95 | 110 | 20 | 225
T36502 | Kingdom Park Phase 2 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2019/20 | October | 56 | 42 | 14 | 0 | 42 |  | 24 | 14 | 4 |  |  | 14 |  | 14 |  |  |  |  | 0 | [6 empty] | 25% | 0% | SR | 2019/20 | January | 2022/23 | September | 3 | 1.432 | [5 empty] | 4.432 |  |  |  | 4.432 | 0.079143 | 50 | 45 | 40 | 70 | 0 | 20 | 95 | 110 | 20 | 225
P44715 | Kingdom Park Phase 3 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2021/22 | November | 87 | 61 | 22 | 4 | 62 | 0 | 28 | 28 | 5 | 1 | 0 | 21 | 0 | 20 | 0 | 0 | 1 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 29.89% | 4.598% | SR | 2021/22 | November | 2024/25 | October |  | 0.5 | 1.717 | 1.916 | 1 |  |  | 5.133 |  |  |  | 5.133 | 0.059 | 50 | 45 | 10 | 70 | 0 | 20 | 95 | 80 | 20 | 195
P41474 | Kirkcaldy SW SDA Phase 1 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | FC | FC | 2023/24 | February | 50 | 35 | 13 | 2 | 32 | 0 | 15 | 15 | 2 | 0 | 0 | 15 | 0 | 13 | 1 | 0 | 1 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 36% | 6% | SR | 2023/24 | February | 2025/26 | February |  |  |  |  | 1.2 | 1.75 |  | 2.95 |  |  |  | 2.95 | 0.059 | 50 | 45 | 10 | 10 | 0 | 20 | 95 | 20 | 20 | 135
P43207 | Park Road | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2019/20 | February | 25 | 23 | 2 | 0 | 23 |  | 15 | 6 | 2 |  |  | 2 |  | 2 |  |  |  |  | 0 | [6 empty] | 8% | 0% | SR | 2019/20 | March | 2021/22 | October | [7 empty] | 0 |  |  |  | 0 | 0 | 50 | 45 | 80 | 70 | 0 | 0 | 95 | 150 | 0 | 245
P44714 | Postings | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2025/26 | April | 25 | 18 | 6 | 1 | 12 | 0 | 5 | 5 | 2 | 0 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 28% | 16% | SR | 2025/26 | April | 2025/26 | March | [5 empty] | 1.475 |  | 1.475 |  |  |  | 1.475 | 0.059 | 50 | 45 | 0 | 30 | 0 | 0 | 95 | 30 | 0 | 125
P41320 | Union Street MS | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | FC | FC | 2022/23 | May | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 100% | SR | 2022/23 | June | 2022/23 | December |  |  | 0.177 |  |  |  |  | 0.177 |  |  |  | 0.177 | 0.059 | 50 | 45 | 50 | 30 | 0 | 0 | 95 | 80 | 0 | 175
P43402 | Viewforth High School | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2021/22 | April | 15 | 11 | 4 |  | 11 |  | 8 | 2 | 1 |  |  | 4 |  | 4 |  |  |  |  | 0 | [6 empty] | 26.67% | 0% | SR | 2021/22 | April | 2021/22 | March |  | 1.17 | [5 empty] | 1.17 |  |  |  | 1.17 | 0.078 | 50 | 45 | 10 | 30 | 0 | 0 | 95 | 40 | 0 | 135
P44713 | Commercial Crescent Ph 3 | Ladybank | Cupar & HOF | Cupar & North West | FC PSD | FC | 2022/23 | April | 11 | 9 | 2 | 0 | 9 | 0 | 0 | 6 | 3 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.18% | 0% | SR | 2022/23 | April | 2022/23 | April |  |  | 0.627 |  |  |  |  | 0.627 |  |  |  | 0.627 | 0.057 | 20 | 15 | 30 | 70 | 0 | 0 | 35 | 100 | 0 | 135
P44712 | High Street | Leslie | Glenrothes | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2021/22 | December | 38 | 28 | 10 | 0 | 28 | 0 | 14 | 10 | 4 | 0 | 0 | 10 | 0 | 8 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.32% | 0% | SR | 2021/22 | December | 2023/24 | June |  | 0.742 | 1.5 |  |  |  |  | 2.242 |  |  |  | 2.242 | 0.059 | 50 | 45 | 0 | 30 | 0 | 0 | 95 | 30 | 0 | 125
T33940 | Ingrie Farm | Leslie | Glenrothes | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2022/23 | April | 45 | 28 | 15 | 2 | 28 |  | 23 | 5 |  |  |  | 14 |  | 12 | 2 |  |  |  | 3 |  | 3 |  |  |  |  | 37.78% | 6.667% | SR | 2022/23 | April | 2023/24 | March |  |  | 3.51 |  |  |  |  | 3.51 |  |  |  | 3.51 | 0.078 | 50 | 45 | 50 | 30 | 0 | 0 | 95 | 80 | 0 | 175
P43378 | Hendersons Meadow | Leuchars | St Andrews | St Andrews & North East | FC | FC | 2023/24 | July | 80 | 56 | 20 | 4 | 56 | 0 | 25 | 25 | 5 | 1 | 0 | 20 | 0 | 19 | 0 | 0 | 1 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 30% | 5% | SR | 2023/24 | July | 2025/26 | July |  |  |  | 2.36 | 2.299 |  |  | 4.659 |  | 0.061 |  | 4.72 | 0.059 | 30 | 50 | 0 | 10 | 0 | 0 | 80 | 10 | 0 | 90
P43196 | Pitlethie Road | Leuchars | St Andrews | St Andrews & North East | KHA | KHA | 2023/24 | October | 49 | 31 | 16 | 2 | 31 |  | 23 | 8 |  |  |  | 14 |  | 12 | 2 |  |  |  | 4 |  | 4 |  |  |  |  | 36.73% | 8.163% | SR | 2023/24 | October | 2024/25 | January | 0.784 |  |  | 1 | 2.038 |  |  | 3.822 |  |  |  | 3.822 | 0.078 | 30 | 50 | 50 | 30 | 0 | 0 | 80 | 80 | 0 | 160
P43915 | Pitlethie Road Phase 2 | Leuchars | St Andrews | St Andrews & North East | KHA | KHA | 2023/24 | April | 46 | 31 | 15 | 0 | 31 |  | 23 | 8 |  |  |  | 15 |  | 13 | 2 |  |  |  | 0 | [6 empty] | 32.61% | 0% | SR | 2023/24 | April | 2024/25 | July | 0.688 |  |  | 2.808 |  |  |  | 3.496 |  |  |  | 3.496 | 0.076 | 30 | 50 | 50 | 30 | 0 | 0 | 80 | 80 | 0 | 160
P44066 | Rosemount Grove | Leven | Levenmouth | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2021/22 | November | 9 | 7 | 2 | 0 | 7 | 2 | 3 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.22% | 0% | SR | 2021/22 | January | 2021/22 | January | 0 | 0.531 | [5 empty] | 0.531 |  |  |  | 0.531 | 0.059 | 50 | 25 | 0 | 70 | 0 | 0 | 75 | 70 | 0 | 145
P44408 | Station Road | Leven | Levenmouth | Kirkcaldy, Glenrothes & Central | KI | KI | 2020/21 | March | 20 | 20 | 0 | 0 | 20 |  | 20 |  |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | MMR 30 | 2020/21 | March | 2022/23 | April | 0.2 | 0.76 | [5 empty] | 0.96 |  |  |  | 0.96 | 0.048 | 50 | 25 | 0 | 70 | 0 | 0 | 75 | 70 | 0 | 145
P41317 | Berry Street MS | Lochgelly | Cowdenbeath | Dunfermline & West | FC | FC | 2022/23 | April | 10 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 100% | 50% | SR | 2022/23 | April | 2022/23 | March |  |  | 0.59 |  |  |  |  | 0.59 |  |  |  | 0.59 | 0.059 | 40 | 25 | 50 | 30 | 0 | 0 | 65 | 80 | 0 | 145
T36562 | Hall Street (Fab-tek Phase 1) | Lochgelly | Cowdenbeath | Dunfermline & West | KHA | OVHA | 2021/22 | January | 34 | 34 |  |  | 34 |  | 17 | 17 |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2021/22 | February | 2023/24 | April |  | 0.1 | 2.484 |  |  |  |  | 2.584 |  |  |  | 2.584 | 0.076 | 40 | 25 | 0 | 30 | 0 | 0 | 65 | 30 | 0 | 95
P41385 | Jenny Gray House | Lochgelly | Cowdenbeath | Dunfermline & West | FC | FC | 2022/23 | March | 40 | 28 | 10 | 2 | 0 | 0 | 13 | 12 | 3 | 0 | 0 | 36 | 0 | 9 | 0 | 0 | 1 | 0 | 4 | 0 | 1 | 1 | 0 | 0 | 0 | 100% | 10% | SR | 2022/23 | March | 2024/25 | February | 0.065 |  |  | 1.295 | 1.8 |  |  | 3.16 |  |  |  | 3.16 | 0.079 | 40 | 25 | 50 | 70 | 20 | 20 | 65 | 120 | 40 | 225
P41449 | Durham Wynd Phase 2 | Lower Largo | Largo & East Neuk | St Andrews & North East | KHA | KHA | 2023/24 | January | 14 | 6 | 8 | 0 | 8 |  | 6 | 2 |  |  |  | 6 |  | 5 |  | 1 |  |  | 0 | [6 empty] | 57.14% | 0% | SR | 2023/24 | January | 2024/25 | February |  |  |  | 1.1 |  |  |  | 1.1 |  |  |  | 1.1 | 0.078571 | 30 | 30 | 0 | 30 | 0 | 0 | 60 | 30 | 0 | 90
P44711 | Lochgelly Road LPH001 | Lumphinnans | Cowdenbeath | Dunfermline & West | FC PSD | FC | 2021/22 | July | 49 | 35 | 12 | 2 | 35 | 0 | 16 | 16 | 3 | 0 | 0 | 12 | 0 | 11 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 28.57% | 4.082% | SR | 2021/22 | August | 2023/24 | July |  | 0.9 | 1 | 0.991 |  |  |  | 2.891 |  |  |  | 2.891 | 0.059 | 40 | 25 | 0 | 30 | 0 | 0 | 65 | 30 | 0 | 95
P44710 | Haig Busness Park | Markinch | Glenrothes | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2023/24 | April | 25 | 18 | 6 | 1 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | 2023/24 | April | 2023/24 | March |  |  |  | 1.475 |  |  |  | 1.475 |  |  |  | 1.475 | 0.059 | 50 | 45 | 10 | 10 | 0 | 0 | 95 | 20 | 0 | 115
TBC | Markinch South (MAR001) | Markinch | Glenrothes | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2022/23 | October | 20 | 15 | 5 | 0 | 15 |  | 11 | 4 |  |  |  | 5 |  | 5 |  |  |  |  | 0 | [6 empty] | 25% | 0% | SR | 2022/23 | October | 2023/24 | December |  |  | 0.68 | 0.5 |  |  |  | 1.18 |  |  |  | 1.18 | 0.059 | 50 | 45 | 10 | 70 | 0 | 0 | 95 | 80 | 0 | 175
P44709 | High Street | Methil | Levenmouth | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2021/22 | October | 10 | 7 | 2 | 1 | 7 | 0 | 3 | 3 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 30% | 10% | SR | 2022/23 | July | 2022/23 | July |  |  | 0.59 |  |  |  |  | 0.59 |  |  |  | 0.59 | 0.059 | 50 | 25 | 0 | 30 | 0 | 0 | 75 | 30 | 0 | 105
P41287 | Kirkland (New Care Village) | Methil | Levenmouth | Kirkcaldy, Glenrothes & Central | FC | FC | 2020/21 | October | 35 | 0 | 27 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 27 | 0 | 0 | 0 | 0 | 8 | 0 | 6 | 2 | 0 | 0 | 0 | 100% | 22.86% | SR | 2020/21 | October | 2023/24 | April | 1.265 | 1 | [5 empty] | 2.265 | 0.5 |  |  | 2.765 | 0.079 | 50 | 25 | 80 | 70 | 20 | 20 | 75 | 150 | 40 | 265
P42648 | Methil Brae Phase 3 | Methil | Levenmouth | Kirkcaldy, Glenrothes & Central | KHA | KHA | 2019/20 | January | 16 | 16 | 0 | 0 | 16 |  | 2 | 8 | 6 |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2019/20 | March | 2021/22 | July | 1.352 | [6 empty] | 1.352 |  |  |  | 1.352 | 0.0845 | 50 | 25 | 80 | 70 | 0 | 0 | 75 | 150 | 0 | 225
P40205 | South of Cupar Road | Newburgh | Tay Coast | Cupar & North West | FC | FC | 2020/21 | March | 34 | 24 | 8 | 2 | 24 | 0 | 11 | 11 | 2 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 29.41% | 5.882% | SR | 2020/21 | March | 2022/23 | June | 0.5 | 1.506 | [5 empty] | 2.006 |  |  |  | 2.006 | 0.059 | 20 | 10 | 0 | 70 | 0 | 0 | 30 | 10 | 0 | 40
P43248 | Land to South of Victoria Park | Newport on Tay | Tay Coast | St Andrews & North East | FC | FC | 2024/25 | April | 20 | 14 | 5 | 1 | 14 | 0 | 7 | 6 | 1 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 30% | 10% | SR | 2024/25 | April | 2025/26 | March |  |  |  |  | 1.18 |  |  | 1.18 |  |  |  | 1.18 | 0.059 | 10 | 10 | 0 | 10 | 0 | 0 | 20 | 30 | 0 | 50
P41485 | Milton Road | Pittenweem | Largo & East Neuk | St Andrews & North East | KHA | KI | 2023/24 | August | 20 | 12 | 7 | 1 | 12 |  | 10 | 2 |  |  |  | 8 |  | 6 |  | 2 |  |  | 0 | [6 empty] | 40% | 0% | MMR 30 | 2023/24 | August | 2024/25 | August |  |  |  | 0.92 |  |  |  | 0.92 |  |  |  | 0.92 | 0.046 | 30 | 30 | 0 | 30 | 0 | 0 | 60 | 30 | 0 | 90
P43399 | off Station Court | Pittenweem | Largo & East Neuk | St Andrews & North East | KHA | KHA | 2022/23 | February | 29 | 18 | 10 | 1 | 18 |  | 14 | 4 |  |  |  | 10 |  | 8 |  | 2 |  |  | 1 |  | 1 |  |  |  |  | 37.93% | 3.448% | SR | 2022/23 | February | 2023/24 | December |  |  | 0.5 | 1.78 |  |  |  | 2.28 |  |  |  | 2.28 | 0.078621 | 30 | 30 | 0 | 30 | 0 | 0 | 60 | 30 | 0 | 90
TBC | Brankholm Brae Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West | FHG | FHG | 2023/24 | April | 38 | 21 | 7 | 2 | 28 |  | 12 | 12 | 4 |  |  | 10 |  | 8 | 1 | 1 |  |  | 0 | [6 empty] | 23.68% | 0% | SR | 2023/24 | April | 2024/25 | December |  |  |  | 1.5 | 1.312 |  |  | 2.812 |  |  |  | 2.812 | 0.074 | 40 | 45 | 0 | 30 | 0 | 0 | 85 | 30 | 0 | 115
P41378 | Castle Road (Recreational Park) | Rosyth | Dunfermline & Coast | Dunfermline & West | FC | FC | 2022/23 | April | 30 | 21 | 7 | 2 | 21 | 0 | 10 | 9 | 2 | 0 | 0 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 6.667% | SR | 2022/23 | May | 2023/24 | April |  |  | 1.6247 |  |  |  |  | 1.6247 |  | 0.145 |  | 1.7697 | 0.058992 | 40 | 45 | 50 | 30 | 0 | 0 | 85 | 80 | 0 | 165
P43854 | Hilton Gardens | Rosyth | Dunfermline & Coast | Dunfermline & West | FC | FC | 2021/22 | April | 45 | 32 | 11 | 2 | 36 | 0 | 14 | 14 | 3 | 0 | 0 | 11 | 0 | 10 | 0 | 0 | 1 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 28.89% | 6.667% | SR | 2021/22 | April | 2022/23 | March |  | 1.255 | 0.7 |  |  |  |  | 1.955 | 0.7 |  |  | 2.655 | 0.059 | 40 | 45 | 30 | 30 | 0 | 0 | 85 | 60 | 0 | 145
P43393 | Park Road | Rosyth | Dunfermline & Coast | Dunfermline & West | KHA | KHA | 2019/20 | March | 23 | 23 | 0 | 0 | 23 |  | 23 |  |  |  |  | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2020/21 | August | 2021/22 | November | 1.747 | [6 empty] | 1.747 |  |  |  | 1.747 | 0.075957 | 40 | 45 | 80 | 70 | 0 | 0 | 85 | 150 | 0 | 235
TBC | Whinnyburn Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West | FHG | FHG | 2025/26 | June | 0 | 18 | 6 | 1 | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2025/26 | August | 2026/27 | August | [5 empty] | 1.35 | 0.5 | 1.85 |  |  |  | 1.85 | 0.074 | 40 | 45 | 0 | 30 | 0 | 0 | 85 | 30 | 0 | 115 | Units to be delivered - 25
P41382 | West Road | Saline | West Fife Villages | Dunfermline & West | FC | FC | 2021/22 | October | 33 | 23 | 8 | 2 | 18 | 0 | 11 | 10 | 2 | 0 | 0 | 13 | 0 | 8 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 45.45% | 6.061% | SR | 2021/22 | October | 2022/23 | December |  | 0.973 | 0.974 |  |  |  |  | 1.947 |  |  |  | 1.947 | 0.059 | 40 | 0 | 0 | 10 | 0 | 0 | 40 | 10 | 0 | 50
P43185 | Crawley Court, Springfield | Springfield | Cupar & HOF | Cupar & North West | FC PSD | FC | 2021/22 | April | 30 | 21 | 5 | 4 | 21 | 0 | 3 | 14 | 4 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 4 | 0 | 3 | 1 | 0 | 0 | 0 | 30% | 13.33% | SR | 2021/22 | April | 2022/23 | November |  | 1 | 0.77 |  |  |  |  | 1.77 |  |  |  | 1.77 | 0.059 | 20 | 15 | 0 | 30 | 0 | 0 | 35 | 30 | 0 | 65
P41506 | Craigtoun (Phase 2) | St Andrews | St Andrews | St Andrews & North East | KHA | KHA | 2024/25 | April | 40 | 27 | 12 | 1 | 25 |  | 18 | 7 |  |  |  | 14 |  | 9 | 5 |  |  |  | 1 |  | 1 |  |  |  |  | 32.5% | 2.5% | SR | 2024/25 | April | 2025/26 | March |  |  |  |  | 2 | 1.04 |  | 3.04 |  |  |  | 3.04 | 0.076 | 30 | 50 | 10 | 30 | 0 | 0 | 80 | 40 | 0 | 120
P41507 | Craigtoun (Phase 3) | St Andrews | St Andrews | St Andrews & North East | KHA | KI | 2024/25 | April | 20 | 14 | 6 | 0 | 14 |  | 11 | 3 |  |  |  | 6 |  | 6 |  |  |  |  | 0 | [6 empty] | 30% | 0% | MMR 30 | 2024/25 | April | 2025/26 | March |  |  |  |  | 0.94 |  |  | 0.94 |  |  |  | 0.94 | 0.047 | 30 | 50 | 10 | 30 | 0 | 0 | 80 | 40 | 0 | 120
P41318 | Forgan Place (Prev Shoolbraids) MS | St Andrews | St Andrews | St Andrews & North East | FC | FC | 2022/23 | May | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | 2022/23 | June | 2022/23 | December |  | 0.118 | [5 empty] | 0.118 |  |  |  | 0.118 | 0.059 | 30 | 50 | 50 | 30 | 0 | 0 | 80 | 80 | 0 | 160
P43392 | Kilrymont Road | St Andrews | St Andrews | St Andrews & North East | FC | FC | 2024/25 | March | 0 | 35 | 12 | 2 | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2025/26 | April | 2026/27 | March | [5 empty] | 2 | 0.891 | 2.891 |  |  |  | 2.891 | 0.059 | 30 | 50 | 50 | 70 | 0 | 20 | 80 | 120 | 20 | 220
P41478 | St Andrews SLA, Craigtoun Phase 1a | St Andrews | St Andrews | St Andrews & North East | FC | FC | 2023/24 | August | 40 | 28 | 10 | 2 | 28 | 0 | 13 | 12 | 3 | 0 | 0 | 10 | 0 | 9 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 5% | SR | 2023/24 | August | 2024/25 | December |  |  |  |  | 0.799 | 0.799 |  | 1.598 | 0.5 | 0.2619 |  | 2.3599 | 0.058997 | 30 | 50 | 0 | 10 | 0 | 20 | 80 | 10 | 20 | 110
P41481 | St Andrews SLA, Craigtoun Phase 1b | St Andrews | St Andrews | St Andrews & North East | FC | FC | 2024/25 | January | 0 | 28 | 10 | 2 | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2024/25 | January | 2026/27 | May | [5 empty] | 1.044 | 1.044 | 2.088 |  | 0.2728 |  | 2.3608 | 0.05902 | 30 | 50 | 0 | 10 | 0 | 20 | 80 | 10 | 20 | 110
T36512 | Mansfield | St Monans | Largo & East Neuk | St Andrews & North East | KHA | KHA | 2018/19 | March | 40 | 26 | 12 | 2 | 26 |  | 14 | 12 |  |  |  | 12 |  | 8 |  | 4 |  |  | 2 |  | 2 |  |  |  |  | 35% | 5% | SR | 2020/21 | February | 2022/23 | October | 0.5 | 2.4 | 0.386 |  |  |  |  | 3.286 |  |  |  | 3.286 | 0.08215 | 30 | 30 | 10 | 70 | 0 | 0 | 60 | 80 | 0 | 140
T36565 | Bonfield Park | Strathkinness | St Andrews | St Andrews & North East | FC PSD | FC | 2022/23 | April | 30 | 20 | 9 | 1 | 20 | 0 | 9 | 8 | 3 | 0 | 0 | 9 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 33.33% | 3.333% | SR | 2022/23 | April | 2023/24 | September |  |  | 1 | 0.567 |  |  |  | 1.567 |  | 0.203 |  | 1.77 | 0.059 | 30 | 50 | 50 | 30 | 0 | 0 | 80 | 80 | 0 | 160
P43391 | Cash Feus Phase 1 | Strathmiglo | Cupar & HOF | Cupar & North West | FC | FC | 2021/22 | June | 19 | 13 | 5 | 1 | 13 | 0 | 6 | 6 | 1 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 31.58% | 5.263% | SR | 2021/22 | June | 2022/23 | December | 0.32 | 0.801 | [5 empty] | 1.121 |  |  |  | 1.121 | 0.059 | 20 | 15 | 50 | 30 | 0 | 0 | 35 | 80 | 0 | 115
P44708 | Cash Feus Phase 2 | Strathmiglo | Cupar & HOF | Cupar & North West | FC | FC | 2023/24 | June | 21 | 15 | 5 | 1 | 15 | 0 | 7 | 7 | 1 | 0 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28.57% | 4.762% | SR | 2022/23 | July | 2023/24 | June |  |  | 0.8 | 0.439 |  |  |  | 1.239 |  |  |  | 1.239 | 0.059 | 20 | 15 | 0 | 30 | 0 | 0 | 35 | 30 | 0 | 65
TBC | Bell Street | Tayport | Tay Coast | St Andrews & North East | KHA | KHA | 2025/26 | April | 0 | 29 | 18 | 2 | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2025/26 | April | 2026/27 | March | [5 empty] | 2 | 1.882 | 3.882 |  |  |  | 3.882 | 0.079224 | 10 | 10 | 0 | 30 | 0 | 0 | 20 | 30 | 0 | 50 | Units to be delivered - 49
P41319 | Links Road MS | Tayport | Tay Coast | St Andrews & North East | FC | FC | 2022/23 | May | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | 2022/23 | June | 2022/23 | December |  |  | 0.118 |  |  |  |  | 0.118 |  |  |  | 0.118 | 0.059 | 10 | 10 | 50 | 70 | 0 | 0 | 20 | 120 | 0 | 140
P41321 | Sandyhill Road (Church Land) | Tayport | Tay Coast | St Andrews & North East | FC | FC | 2022/23 | April | 24 | 0 | 20 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 100% | 16.67% | SR | 2022/23 | April | 2023/24 | May |  |  | 1.5 | 0.396 |  |  |  | 1.896 |  |  |  | 1.896 | 0.079 | 10 | 10 | 0 | 30 | 0 | 0 | 20 | 30 | 0 | 50
P43406 | Memorial Park | Thornton | Glenrothes | Kirkcaldy, Glenrothes & Central | KI | KI | 2023/24 | June | 25 | 18 | 7 | 0 | 18 |  | 14 | 4 |  |  |  | 7 |  | 6 |  | 1 |  |  | 0 | [6 empty] | 28% | 0% | MMR 30 | 2023/24 | June | 2024/25 | June |  |  |  | 1.15 |  |  |  | 1.15 |  |  |  | 1.15 | 0.046 | 50 | 45 | 0 | 30 | 0 | 0 | 95 | 30 | 0 | 125
P44707 | Strathore Road (Thornton SLA) | Thornton | Glenrothes | Kirkcaldy, Glenrothes & Central | FC PSD | FC | 2024/25 | November | 0 | 35 | 12 | 2 | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0% | 0% | SR | 2024/25 | December | 2026/27 | November |  |  |  |  | 0.5 | 1.691 |  | 2.191 | 0.7 |  |  | 2.891 | 0.059 | 50 | 45 | 0 | 30 | 0 | 20 | 95 | 30 | 20 | 145
P41444 | Main Street | Torryburn | West Fife Villages | Dunfermline & West | KHA | KHA | 2020/21 | January | 4 | 3 | 1 |  | 3 |  | 3 |  |  |  |  | 1 |  | 1 |  |  |  |  | 0 | [6 empty] | 25% | 0% | SR | 2020/21 | February | 2021/22 | October | 0.35 | [6 empty] | 0.35 |  |  |  | 0.35 | 0.0875 | 40 | 0 | 80 | 70 | 0 | 0 | 40 | 150 | 0 | 190
T36558 | Kilmany Road Phase 2 | Wormit | Tay Coast | St Andrews & North East | KHA | KHA | 2021/22 | December | 50 | 38 | 12 |  | 38 |  | 24 | 14 |  |  |  | 12 |  | 8 | 4 |  |  |  | 0 | [6 empty] | 24% | 0% | SR | 2021/22 | December | 2022/23 | March |  | 1 | 2.9 |  |  |  |  | 3.9 |  |  |  | 3.9 | 0.078 | 10 | 10 | 40 | 70 | 0 | 0 | 20 | 110 | 0 | 130
[9 empty] | 3859 |  |  |  | 2690 | [6 empty] | 988 | [6 empty] | 183 | [6 empty] | 30.34% | 4.742% | [5 empty] | 36.414 | 51.61 | 54.8383 | 46.754 | 39.071 | 42.861 | 8.9338 | 280.4821 | 7.75 | 1.1766 |  | 289.4087

## HNDA
LHS Area | Annual Need - HNDA | 5 Year Need - HNDA | 10 Year Need - HNDA | Total Programme | Completed | Oversupply/ (Shortfall) (5 Year Need) | % of 5 Year Need | Oversupply/ (Shortfall) (10 Year Need) | % of 10 Year Need | Potential | Oversupply/ (Shortfall) inc. potential (5 Year Need) | % of 5 Year Need | Oversupply/ (Shortfall) inc. potential (10 Year Need) | % of 10 Year Need | Programmed | Oversupply/ (Shortfall) inc. programmed (5 Year Need) | % of 5 Year Need | Oversupply/ (Shortfall) inc. potential (10 Year Need) | % of 10 Year Need
Cowdenbeath | 54 | 270 | 540 | 240 | #REF! | -30 | 88.89% | -300 | 44.44% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Cupar & HOF | 39 | 195 | 390 | 181 | #REF! | -14 | 92.82% | -209 | 46.41% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Dunf & Coast | 139 | 695 | 1390 | 705 | #REF! | 10 | 101.4% | -685 | 50.72% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Glenrothes | 78 | 390 | 780 | 475 | #REF! | 85 | 121.8% | -305 | 60.9% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Kirkcaldy | 114 | 570 | 1140 | 536 | #REF! | -34 | 94.04% | -604 | 47.02% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Largo & East Neuk | 26 | 130 | 260 | 66 | #REF! | -64 | 50.77% | -194 | 25.38% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Levenmouth | 56 | 280 | 560 | 108 | #REF! | -172 | 38.57% | -452 | 19.29% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
St Andrews | 40 | 200 | 400 | 288 | #REF! | 88 | 144% | -112 | 72% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Tay Coast | 22 | 110 | 220 | 30 | #REF! | -80 | 27.27% | -190 | 13.64% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
West Fife Villages | 26 | 130 | 260 | 206 | #REF! | 76 | 158.5% | -54 | 79.23% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Fife Wide/Total | 594 | 2970 | 5940 | 2835 |  | -135 | 95.45% | -3105 | 47.73% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Estimated Housing Need and Demand / Average Annualised 2017-32 by LHSA
Based on Census 2011 and 2014 based household projections using Knowfife to disaggregate households / disaggregation of homes from TAYplan & SESplan levels
The need figures by LHS Area are ‘indicative’.

## Codes
This sheet has all the options for the dropdown lists on the main sheet. Blank rows have been left to allow extra options to be added in the future - please do not delete them.
SLP Status
17/18
18/19
19/20
20/21
21/22
22/23
23/24
Developer
FC
FC PSD
KHA
KI
FHG
Landlord
FC
FC PSD
KHA
KI
FHG (A)
OVHA
GHA
FHG
LHS Area
Glenrothes
Kirkcaldy
Levenmouth
Dunfermline & Coast
Cowdenbeath
West Fife Villages
Cupar & HOF
Largo & East Neuk
St Andrews
Tay Coast
SG Tender Approval Year
2017/18
2018/19
2019/20
2020/21
2021/22
2022/23
2023/24
2024/25
2025/26
2026/27
2027/28
2028/29
Tenure
SR
MMR 30
MMR 5
PSR
Other
Contract Type
D&B
OTS
FC BS
Staged
Change Control
Add - to be approved
Removed - to be approved
Other Change - lead delivery partner
Other Change - see comments
Stage
0 - Feasibility
1 - Dev Mix & brief
2 - design, plg & acq
3 - tender approval
4 - on site
5 - completed
Block
A
B
Shadow
Lead Officer
S Kirkpatrick
J Watson
A Henderson
M Glennie
C Hunter
A Kennedy
D Robertson
HMA
Dunfermline & West
Kirkcaldy, Glenrothes & Central
Cupar & North West
St Andrews & North East