## SHIP WD
STRATEGIC HOUSING INVESTMENT PLAN - FIFE (YEAR 2025/26 - 2029/30)
SHIP Projects Table | [72 empty] | HIDE
HARP Ref | Project Name | Town | LHS Area | HMA | AHP Requirement Site | Developer | Landlord | SG Tender Approval Year | SG Approval Month | Total Unit Numbers | General Needs Units | Amenity Units | Wheelchair Units | Total Bedsapces | General Needs Bedspaces | Amenity Bedspaces | Wheelchair Bedspaces | TOTAL GN Units | GN - 1 bed | GN - 2 bed | GN - 3 bed | GN - 4 bed | GN - 5 bed | GN - 6+ bed | TOTAL AM Units | AM - 1 bed | AM - 2 bed | AM - 3 bed | AM - 4 bed | AM - 5 bed | AM - 6+ bed | TOTAL Wheelchair Units | WC - 1 bed | WC - 2 bed | WC - 3 bed | WC - 4 bed | WC - 5 bed | WC - 6+ bed | % SN Units (AM+WH) | % WH Units | Tenure | Contract Type | Est/Actual site start year | Est/Actual site start month | Est/Actual Comp Year | Est/Actual Comp Month | SG Grant Pre 2025/26 | SG Grant 2025/2026 (£m) | SG Grant 2026/2027 (£m) | SG Grant 2027/2028 (£m) | SG Grant 2028/29 (£m) | SG Grant 2029/30 (£m) | SG Grant Post 2029/2030 (£m) | Total SG Funding | Total Greener Standards Funding (Y/N ) | Charitable Bond | Total 2HCT (£m) | Total FC Commuted Sums (£m) | Total Subsidy (£m) | Total Subsidy per unit (£m) | HMA Need | LHSA Need | DD - Planning & Land | DD - Devt Status | SF - Wider Objectives | SF - Equualities | Housing Need Total | Devt Deliver Total | Strategic Fit Total | SHIP Priority Total | Priority (LMH) | Comment | unit comment
P47652 | Main Street | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | September | 21 | 15 | 6 | 0 | 84 | 60 | 24 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.57% | 0% | SR | D&B | 2024/25 | November | 2026/27 | April |  | 1.0551 | [5 empty] | 1.0551 |  |  | 1 |  | 2.0551 | 0.09786 | 40 | 20 | 40 | 70 | 0 | 10 | 60 | 110 | 10 | 180 | H
P47804 | Hillside School Phase 1 MMR KHA | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | KI | KI | 2027/28 | May | 11 | 11 | 0 | 0 | 49 | 49 | 0 | 0 | 11 | 0 | 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | May | 2028/29 | April |  |  |  | 0.902 |  |  |  | 0.902 |  |  |  |  | 0.902 | 0.082 | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110 | L
P46103 | Hillside School Phase 2 FC SR | Aberdour | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2029/30 | May | 0 | 0 | 0 | 0 | 0 | 88 | 54 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | May | 2031/32 | April | [5 empty] | 0.7 | 2.6162 | 3.3162 |  |  |  |  | 3.3162 | 0.094749 | 40 | 20 | 0 | 30 | 0 | 20 | 60 | 30 | 20 | 110 | L | 35 units to be delivered | 35
P43380 | Ladywalk (Former Care Home) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 0 | 0 | 0 | 0 | 0 | 31 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | April | 2030/31 | December | [5 empty] | 0.7 | 1.195 | 1.895 | Y |  |  |  | 1.895 | 0.094749 | 30 | 25 | 50 | 30 | 20 | 20 | 55 | 80 | 40 | 175 | M | 20 units to be delivered | 20
P43379 | Mayview Court (New Care Village) | Anstruther | Largo & East Neuk | St Andrews & East Fife | No | FC | FC | 2025/26 | October | 14 | 0 | 10 | 4 | 41 | 0 | 25 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 5 | 5 | 0 | 0 | 0 | 0 | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 100% | 28.57% | SR | D&B | 2025/26 | October | 2027/28 | August |  | 0.663 | 0.263 |  |  |  |  | 0.926 | Y |  | 0.4 |  | 1.326 | 0.094714 | 30 | 25 | 50 | 30 | 20 | 30 | 55 | 80 | 50 | 185 | H
P43195 | Carswell Wynd | Auchtermuchty | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2027/28 | March | 30 | 19 | 10 | 1 | 122 | 76 | 42 | 4 | 19 | 0 | 14 | 5 | 0 | 0 | 0 | 10 | 0 | 9 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 36.67% | 3.333% | SR | D&B | 2027/28 | March | 2029/30 | November |  |  |  | 0.6 | 1.169 | 1.169 |  | 2.938 |  |  |  |  | 2.938 | 0.097933 | 20 | 45 | 0 | 10 | 0 | 10 | 65 | 10 | 10 | 85 | L
P47093 | Kirklands Farm Phase 4 | Ballingry | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2028/29 | January | 0 | 0 | 0 | 0 | 0 | 79 | 89 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | January | 2030/31 | March |  |  |  |  | 0.5 | 3.418 |  | 3.918 |  |  |  |  | 3.918 | 0.09795 | 40 | 5 | 0 | 10 | 0 | 10 | 45 | 10 | 10 | 65 | L | 40 units to be delivered | 40
P41440 | Main Street | Balmullo | St Andrews | St Andrews & East Fife | Yes | KHA | KHA | 2024/25 | September | 19 | 16 | 2 | 1 | 78 | 60 | 14 | 4 | 16 | 0 | 9 | 6 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 15.79% | 5.263% | SR | D&B | 2024/25 | September | 2025/26 | September |  | 2.166 | [5 empty] | 2.166 |  |  |  |  | 2.166 | 0.114 | 30 | 50 | 10 | 30 | 0 | 10 | 80 | 40 | 10 | 130 | L
P44701 | Land to North of South Avenue | Blairhall | West Fife Villages | Dunfermline & West Fife | No | FC PSD | FC | 2029/30 | January | 0 | 0 | 0 | 0 | 0 | 80 | 70 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | January | 2031/32 | October | [5 empty] | 0.2 | 1.221 | 1.421 | Y |  |  |  | 1.421 | 0.094733 | 40 | 10 | 0 | 10 | 0 | 20 | 50 | 10 | 20 | 80 | L | 15 units to be delivered | 15
P46139 | Conscience Bridge | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | January | 18 | 13 | 4 | 1 | 86 | 62 | 20 | 4 | 13 | 0 | 6 | 4 | 3 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 27.78% | 5.556% | SR | D&B | 2024/25 | January | 2026/27 | September |  | 1.2573 | [5 empty] | 1.2573 | Y |  | 0.4 | 0.048167 | 1.7055 | 0.094749 | 40 | 10 | 10 | 30 | 0 | 20 | 50 | 40 | 20 | 110 | L
P45308 | Pitdinnie Road Phase 2 | Cairneyhill | West Fife Villages | Dunfermline & West Fife | Yes | KHA | KHA | 2027/28 | January | 0 | 0 | 0 | 0 | 0 | 204 | 56 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2027/28 | January | 2030/31 | November |  |  |  | 2.5 | 1.671 |  |  | 4.171 | Y |  |  |  | 4.171 | 0.066206 | 40 | 10 | 40 | 70 | 0 | 10 | 50 | 110 | 10 | 170 | M | 63 units to be delivered | 63
T34135 | Main Street | Carnock | West Fife Villages | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | July | 0 | 0 | 0 | 0 | 0 | 76 | 42 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | July | 2031/32 | March | 0.314 |  |  |  |  | 1.938 | 1 | 3.252 |  |  |  |  | 3.252 | 0.1084 | 40 | 10 | 50 | 30 | 0 | 10 | 50 | 80 | 10 | 140 | M | 30 units to be delivered | 30
P43400 | Millburn Avenue | Coaltown Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2027/28 | January | 10 | 10 | 0 | 0 | 40 | 40 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2027/28 | January | 2028/29 | March |  |  |  | 0.49 |  |  |  | 0.49 |  |  |  |  | 0.49 | 0.049 | 50 | 20 | 10 | 30 | 0 | 10 | 70 | 40 | 10 | 120 | L
T36573 | Main Street | Colinsburgh | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2024/25 | November | 6 | 4 | 0 | 2 | 27 | 19 | 0 | 8 | 4 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 33.33% | 33.33% | SR | D&B | 2024/25 | November | 2025/26 | July |  | 0.684 | [5 empty] | 0.684 |  |  |  |  | 0.684 | 0.114 | 30 | 25 | 30 | 70 | 0 | 10 | 55 | 100 | 10 | 165 | M
T36507 | High Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2029/30 | March | 0 | 0 | 0 | 0 | 0 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | March | 2031/32 | October | [5 empty] | 0.1 | 2.771 | 2.871 | Y |  |  |  | 2.871 | 0.099 | 40 | 5 | 0 | 30 | 20 | 10 | 45 | 30 | 30 | 105 | L | 29 units to be delivered | 29
P47779 | King Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2025/26 | September | 11 | 6 | 0 | 5 | 47 | 24 | 0 | 23 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 2 | 3 | 0 | 0 | 0 | 45.45% | 45.45% | SR | D&B | 2025/26 | September | 2026/27 | April |  | 1.0422 | [5 empty] | 1.0422 |  |  |  |  | 1.0422 | 0.094749 | 40 | 5 | 0 | 30 | 20 | 30 | 45 | 30 | 50 | 125 | L
P41381 | Valley House, Hill Street | Cowdenbeath | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2021/22 | January | 19 | 12 | 6 | 1 | 94 | 58 | 32 | 4 | 12 | 0 | 6 | 4 | 2 | 0 | 0 | 6 | 0 | 4 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 36.84% | 5.263% | SR | D&B | 2024/25 | April | 2025/26 | September | 1.1789 | [6 empty] | 1.1789 | Y |  | 0.5 |  | 1.6789 | 0.088364 | 40 | 5 | 80 | 70 | 0 | 20 | 45 | 150 | 20 | 215 | H
P41484 | Pitconochie Farm | Crossford | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2026/27 | January | 53 | 35 | 17 | 1 | 216 | 140 | 72 | 4 | 35 | 0 | 27 | 8 | 0 | 0 | 0 | 17 | 0 | 15 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 33.96% | 1.887% | SR | D&B | 2026/27 | January | 2029/30 | March |  |  | 0.834 | 3.833 |  |  |  | 4.667 |  |  |  |  | 4.667 | 0.088057 | 40 | 20 | 40 | 70 | 0 | 10 | 60 | 110 | 10 | 180 | H
P41457 | Manse Road (CRO002) | Crossgates | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2026/27 | June | 11 | 7 | 3 | 1 | 46 | 30 | 12 | 4 | 7 | 0 | 5 | 2 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 36.36% | 9.091% | SR | D&B | 2026/27 | June | 2027/28 | November |  |  | 0.74224 |  |  |  |  | 0.74224 | Y |  | 0.3 |  | 1.0422 | 0.094749 | 40 | 5 | 0 | 10 | 0 | 20 | 45 | 10 | 20 | 75 | L
P41314 | Inchgall Avenue MS | Crosshill | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 4 | 0 | 0 | 4 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | [5 empty] | 0.379 |  | 0.379 | Y |  |  |  | 0.379 | 0.094749 | 40 | 5 | 50 | 10 | 20 | 30 | 45 | 60 | 50 | 155 | M
P41491 | Cupar North (Phase1A) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2028/29 | April | 0 | 0 | 0 | 0 | 0 | 72 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March |  |  |  |  | 2.448 |  |  | 2.448 |  |  |  |  | 2.448 | 0.09792 | 20 | 45 | 10 | 30 | 20 | 10 | 65 | 40 | 30 | 135 | M | 25 units to be delivered | 25
P41492 | Cupar North (Phase1B) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2028/29 | April | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2028/29 | April | 2030/31 | March |  |  |  |  | 0.416 |  |  | 0.416 |  |  |  |  | 0.416 | 0.069333 | 20 | 45 | 10 | 30 | 20 | 10 | 65 | 40 | 30 | 135 | M | 6 units to be delivered | 6
P44702 | Dalgairn (New Care Village) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2024/25 | July | 12 | 0 | 12 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2023/24 | November | 2025/26 | August | 0.35 | 0.57898 | [5 empty] | 0.92898 | Y |  |  | 0.0331 | 0.96208 | 0.080174 | 20 | 45 | 50 | 70 | 20 | 30 | 65 | 120 | 50 | 235 | H
P41467 | Gilliesfaulds Phase 1 (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2027/28 | April | 13 | 6 | 7 | 0 | 60 | 24 | 36 | 0 | 6 | 0 | 2 | 4 | 0 | 0 | 0 | 7 | 0 | 3 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.85% | 0% | SR | D&B | 2027/28 | April | 2028/29 | March |  |  |  | 1.274 |  |  |  | 1.274 | Y |  |  |  | 1.274 | 0.098 | 20 | 45 | 10 | 30 | 0 | 10 | 65 | 40 | 10 | 115 | L
P41477 | Gilliesfaulds Phase 2 - (MMR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KI | 2029/30 | June | 0 | 0 | 0 | 0 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | June | 2031/32 | February | [5 empty] | 0.832 |  | 0.832 |  |  |  |  | 0.832 | 0.069333 | 20 | 45 | 10 | 30 | 0 | 10 | 65 | 40 | 10 | 115 | L | 12 units to be delivered | 12
P41479 | Gilliesfaulds Phase 2 - (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | Yes | KHA | KHA | 2029/30 | June | 0 | 0 | 0 | 0 | 0 | 106 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | June | 2031/32 | February | [5 empty] | 0.6 | 3.123 | 3.723 |  |  |  |  | 3.723 | 0.097974 | 20 | 45 | 10 | 30 | 0 | 10 | 65 | 40 | 10 | 115 | L | 38 units to be delivered | 38
P45310 | Inner Court (SR) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC PSD | FC | 2025/26 | May | 10 | 10 | 0 | 0 | 40 | 40 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | May | 2026/27 | August |  | 0.64749 | [5 empty] | 0.64749 | Y |  | 0.6 |  | 1.2475 | 0.12475 | 20 | 45 | 30 | 70 | 20 | 10 | 65 | 100 | 30 | 195 | H
P44735 | Inner Court (MMR) | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KI | 2025/26 | May | 13 | 13 | 0 | 0 | 48 | 48 | 0 | 0 | 13 | 2 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | May | 2026/27 | October |  | 0.901 | [5 empty] | 0.901 | Y |  |  | 0.0132 | 0.9142 | 0.070323 | 20 | 45 | 80 | 70 | 20 | 10 | 65 | 150 | 30 | 245 | H
P41458 | North Eden (Former Care Home) | Cupar | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2026/27 | June | 20 | 14 | 4 | 2 | 94 | 66 | 20 | 8 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 30% | 10% | SR | D&B | 2026/27 | June | 2027/28 | May |  |  | 1.895 |  |  |  |  | 1.895 | Y |  |  |  | 1.895 | 0.094749 | 20 | 45 | 50 | 30 | 20 | 20 | 65 | 80 | 40 | 185 | H
P45404 | Pitscottie Road, Phase 4 | Cupar | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2026/27 | June | 49 | 34 | 12 | 3 | 245 | 172 | 60 | 13 | 34 | 0 | 6 | 20 | 8 | 0 | 0 | 12 | 0 | 8 | 0 | 4 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30.61% | 6.122% | SR | D&B | 2026/27 | October | 2029/30 | April | 0.59819 |  | 1.702 | 2.5 |  |  |  | 4.8002 | Y |  |  |  | 4.8002 | 0.097963 | 20 | 45 | 50 | 30 | 0 | 20 | 65 | 80 | 20 | 165 | M
P45405 | Trynmuir Phase 2 | Cuparmuir | Cupar & HOF | Cupar & North West Fife | No | KHA | KHA | 2028/29 | December | 0 | 0 | 0 | 0 | 0 | 56 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | December | 2030/31 | March |  |  |  |  | 0.3 | 1.659 |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | 20 | 45 | 0 | 30 | 0 | 10 | 65 | 30 | 10 | 105 | L | 20 units to be delivered | 20
P46448 | Fulmar Way | Dalgety Bay | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2025/26 | April | 9 | 7 | 2 | 0 | 38 | 30 | 8 | 0 | 7 | 0 | 5 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.22% | 0% | SR | D&B | 2025/26 | April | 2026/27 | March |  | 0.882 | [5 empty] | 0.882 | Y |  |  |  | 0.882 | 0.098 | 40 | 20 | 40 | 70 | 0 | 10 | 60 | 110 | 10 | 180 | M
P46874 | Aberdour Road / Evershed Drive (EC Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2025/26 | April | 40 | 0 | 27 | 13 | 93 | 0 | 60 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 21 | 6 | 0 | 0 | 0 | 0 | 13 | 6 | 7 | 0 | 0 | 0 | 0 | 100% | 32.5% | SR | D&B | 2025/26 | April | 2026/27 | November |  | 1.79 | 2 |  |  |  |  | 3.79 | Y |  |  |  | 3.79 | 0.09475 | 40 | 20 | 0 | 30 | 20 | 30 | 60 | 30 | 50 | 140 | M
P45413 | Bellyeoman Road (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | November | 45 | 15 | 18 | 12 | 163 | 90 | 43 | 30 | 15 | 0 | 0 | 15 | 0 | 0 | 0 | 18 | 11 | 7 | 0 | 0 | 0 | 0 | 12 | 6 | 6 | 0 | 0 | 0 | 0 | 66.67% | 26.67% | SR | D&B | 2022/23 | January | 2026/27 | September | 3.4471 | [5 empty] | 0.18 | 3.6271 | Y |  |  | 0.20525 | 3.8323 | 0.085163 | 40 | 20 | 80 | 70 | 20 | 30 | 60 | 150 | 50 | 260 | H
P41465 | Blacklaw Road Phase 2 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC | FC | 2021/22 | February | 85 | 66 | 13 | 6 | 453 | 333 | 94 | 26 | 66 | 0 | 25 | 27 | 14 | 0 | 0 | 13 | 0 | 1 | 2 | 0 | 10 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 22.35% | 7.059% | SR | D&B | 2023/24 | February | 2026/27 | May | 7.6645 | [6 empty] | 7.6645 | Y |  |  |  | 7.6645 | 0.090171 | 40 | 20 | 80 | 70 | 0 | 10 | 60 | 150 | 10 | 220 | H
P41503 | Broomhall (Phase 1) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KI | 2028/29 | July | 0 | 0 | 0 | 0 | 0 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2028/29 | July | 2030/31 | January | 0.64835 |  |  |  | 1.336 | 1.5 |  | 3.4843 |  |  |  |  | 3.4843 | 0.065742 | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | H | 53 units to be delivered | 53
P41504 | Broomhall (Phase 2) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | November | 0 | 0 | 0 | 0 | 0 | 147 | 61 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | March | 2032/33 | October | 0.69637 |  |  |  |  | 0.3 | 3.7 | 4.6964 |  |  |  |  | 4.6964 | 0.080972 | 40 | 20 | 60 | 70 | 20 | 20 | 60 | 130 | 40 | 230 | H | 58 units to be delivered | 58
P41459 | Carnock Road (Former Milesmark Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | November | 12 | 10 | 2 | 0 | 54 | 46 | 8 | 0 | 10 | 0 | 4 | 6 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.67% | 0% | SR | D&B | 2024/25 | November | 2025/26 | November |  | 1.137 | [5 empty] | 1.137 | Y |  |  |  | 1.137 | 0.09475 | 40 | 20 | 30 | 30 | 20 | 10 | 60 | 60 | 30 | 150 | M
P45412 | Elgin Street (Former Depot) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2024/25 | November | 44 | 32 | 8 | 4 | 211 | 134 | 61 | 16 | 32 | 0 | 26 | 6 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 2 | 6 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 27.27% | 9.091% | SR | D&B | 2024/25 | January | 2026/27 | January | 1.2 | 2.1492 | [5 empty] | 3.3492 | Y |  | 0.8 | 0.0198 | 4.169 | 0.094749 | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180 | H
P46393 | Golfdrum Street | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | January | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | January | 2030/31 | May | [5 empty] | 0.558 | 0.202 | 0.76 |  |  |  |  | 0.76 | 0.095 | 40 | 20 | 50 | 30 | 20 | 20 | 60 | 80 | 40 | 180 | H | 8 units to be delivered | 8
P46174 | James Bank Hostel Redevelopment | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KHA | 2025/26 | July | 20 | 20 | 0 | 0 | 67 | 67 | 0 | 0 | 20 | 1 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | July | 2026/27 | March |  | 1.62 | [5 empty] | 1.62 |  |  |  |  | 1.62 | 0.081 | 40 | 20 | 50 | 70 | 20 | 10 | 60 | 120 | 30 | 210 | H
P47365 | New City House | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2024/25 | October | 32 | 32 | 0 | 0 | 134 | 134 | 0 | 0 | 32 | 0 | 17 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2024/25 | October | 2025/26 | December | 1.5 | 1.444 | [5 empty] | 2.944 |  |  |  |  | 2.944 | 0.092 | 40 | 20 | 80 | 70 | 20 | 10 | 60 | 150 | 30 | 240 | H
P41462 | North Fod Phase 2 (EC Housing) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2027/28 | April | 44 | 0 | 40 | 4 | 132 | 0 | 104 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 14 | 26 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2027/28 | April | 2028/29 | December | 1.25 |  |  | 0.1 | 1.869 |  |  | 3.219 | Y |  | 0.95 |  | 4.169 | 0.09475 | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170 | M
P46392 | North Fod Phase 3 | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2028/29 | January | 0 | 0 | 0 | 0 | 0 | 219 | 46 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | FC BS | 2028/29 | January | 2030/31 | April | 0.75 |  |  |  | 1 | 2.0927 |  | 3.8427 |  |  | 0.8 |  | 4.6427 | 0.094749 | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160 | M | 49 units to be delivered | 49
P45410 | South Castle Drive | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2029/30 | August | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | September | 2030/31 | October | [5 empty] | 1.248 |  | 1.248 |  |  |  |  | 1.248 | 0.069333 | 40 | 20 | 0 | 10 | 0 | 10 | 60 | 10 | 10 | 80 | L | 18 units to be delivered | 18
P47094 | Townhill Road (DUN038) CB | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2023/24 | March | 16 | 11 | 4 | 1 | 75 | 51 | 20 | 4 | 11 | 0 | 6 | 3 | 2 | 0 | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 31.25% | 6.25% | SR | D&B | 2023/24 | March | 2025/26 | June | [7 empty] | 0 | Y | 1.91 | 0.131 | 0.09 | 2.131 | 0.13319 | 40 | 20 | 40 | 70 | 0 | 20 | 60 | 110 | 20 | 190 | H
P46875 | Walmer Drive | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2029/30 | January | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | January | 2031/32 | August | [5 empty] | 0.2 | 2.2635 | 2.4635 |  |  |  |  | 2.4635 | 0.094749 | 40 | 20 | 10 | 30 | 20 | 10 | 60 | 40 | 30 | 130 | L | 26 units to be delivered | 26
P43286 | Wester Whitefield (Halbeath SDA) | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2027/28 | April | 93 | 70 | 20 | 3 | 392 | 300 | 80 | 12 | 70 | 0 | 52 | 16 | 2 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 24.73% | 3.226% | SR | D&B | 2027/28 | April | 2029/30 | January |  |  |  | 3 | 3 | 2.0617 |  | 8.0617 | Y |  | 0.75 |  | 8.8117 | 0.094749 | 40 | 20 | 10 | 30 | 20 | 20 | 60 | 40 | 40 | 140 | M
P43377 | Woodmill Street MS | Dunfermline | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2028/29 | June | 6 | 0 | 3 | 3 | 24 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 50% | SR | D&B | 2028/29 | June | 2029/30 | December |  |  |  |  | 0.56849 |  |  | 0.56849 | Y |  |  |  | 0.56849 | 0.094749 | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170 | M
P43199 | Boreland Road | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2026/27 | July | 34 | 24 | 10 | 0 | 170 | 122 | 48 | 0 | 24 | 0 | 10 | 2 | 12 | 0 | 0 | 10 | 0 | 8 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29.41% | 0% | SR | D&B | 2026/27 | April | 2027/28 | September |  |  | 1.2 | 1.3215 |  |  |  | 2.5215 | Y |  | 0.7 |  | 3.2215 | 0.094749 | 50 | 30 | 30 | 30 | 0 | 20 | 80 | 60 | 20 | 160 | M
P46105 | Howard Place 2 (Including Regen of 61-103 HP) | Dysart | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | June | 19 | 13 | 5 | 1 | 89 | 61 | 24 | 4 | 13 | 0 | 6 | 5 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 31.58% | 5.263% | SR | D&B | 2025/26 | June | 2026/27 | January |  |  | 1.305 |  |  |  |  | 1.305 | Y |  | 0.5 |  | 1.805 | 0.095 | 50 | 30 | 50 | 30 | 20 | 20 | 80 | 80 | 40 | 200 | H
P41450 | Wadeslea | Elie | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2027/28 | June | 12 | 8 | 4 | 0 | 42 | 24 | 18 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.33% | 0% | SR | D&B | 2027/28 | November | 2028/29 | January |  |  |  | 0.588 | 0.588 |  |  | 1.176 |  |  |  |  | 1.176 | 0.098 | 30 | 25 | 10 | 10 | 0 | 10 | 55 | 20 | 10 | 85 | L
P44705 | Open Market Transactions 25/26 | Fife | Fife | Fife | No | FC | FC | 2025/26 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2025/26 | April | 2025/26 | March |  | 2.5 | [5 empty] | 2.5 |  |  |  |  | 2.5 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
P45414 | Open Market Transactions 26/27 | Fife | Fife | Fife | No | FC | FC | 2026/27 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2026/27 | April | 2026/27 | March |  |  | 2.5 |  |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
P46084 | Open Market Transactions 27/28 | Fife | Fife | Fife | No | FC | FC | 2027/28 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2027/28 | April | 2027/28 | March |  |  |  | 2.5 |  |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
P46934 | Open Market Transactions 28/29 | Fife | Fife | Fife | No | FC | FC | 2028/29 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2028/29 | April | 2028/29 | March |  |  |  |  | 2.5 |  |  | 2.5 |  |  |  |  | 2.5 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
P47778 | Open Market Transactions 29/30 | Fife | Fife | Fife | No | FC | FC | 2029/30 | April | 50 | 50 | 0 | 0 | 200 | 200 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2029/30 | April | 2029/30 | March | [5 empty] | 2.5 |  | 2.5 |  |  |  |  | 2.5 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
P45420 | Main Road (Retirement Housing) | Gauldry | Tay Coast | Greater Dundee | No | FC PSD | FC | 2026/27 | December | 22 | 0 | 20 | 2 | 88 | 0 | 80 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 9.091% | SR | D&B | 2026/27 | December | 2027/28 | December |  |  | 1.0845 | 1 |  |  |  | 2.0845 | Y |  |  |  | 2.0845 | 0.094749 | 30 | 40 | 0 | 30 | 20 | 30 | 70 | 30 | 50 | 150 | M
P44703 | Alexander Road (Regen) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2029/30 | September | 0 | 0 | 0 | 0 | 0 | 96 | 33 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | September | 2030/31 | December | [5 empty] | 1.1477 | 1 | 2.1477 | Y |  | 0.6 |  | 2.7477 | 0.094749 | 50 | 20 | 50 | 30 | 20 | 20 | 70 | 80 | 40 | 190 | H | 29 units to be delivered | 29
P41471 | Glenwood Centre Regeneration (FC) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | August | 19 | 0 | 19 | 0 | 76 | 0 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | SR | D&B | 2025/26 | August | 2026/27 | January |  | 0.5 | 0.85093 |  |  |  |  | 1.3509 | Y |  | 0.4 | 0.0493 | 1.8002 | 0.094749 | 50 | 20 | 50 | 30 | 20 | 20 | 70 | 80 | 40 | 190 | H
P46175 | Glenwood Centre Regeneration (KHA) SR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | August | 12 | 12 | 0 | 0 | 88 | 88 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | August | 2026/27 | January |  | 0.5 | 0.688 |  |  |  |  | 1.188 | Y |  |  |  | 1.188 | 0.099 | 50 | 20 | 50 | 30 | 20 | 20 | 70 | 80 | 40 | 190 | H
P47800 | Glenwood Centre Regeneration (KHA) MMR | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2025/26 | August | 12 | 12 | 0 | 0 | 88 | 88 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | August | 2026/27 | January |  | 0.25 | 0.722 |  |  |  |  | 0.972 | Y |  |  |  | 0.972 | 0.081 | 50 | 20 | 50 | 30 | 20 | 20 | 70 | 80 | 40 | 190 | H
P46876 | Leven Mill, Queensgate (OTS) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2024/25 | May | 17 | 17 | 0 | 0 | 70 | 70 | 0 | 0 | 17 | 0 | 6 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | OTS | 2023/24 | October | 2025/26 | April |  | 0.69226 | [5 empty] | 0.69226 | Y |  | 1 |  | 1.6923 | 0.099545 | 50 | 20 | 30 | 30 | 0 | 10 | 70 | 60 | 10 | 140 | M
P41393 | Napier Road, (Former Police Station) (OTS) | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2025/26 | April | 4 | 4 | 0 | 0 | 18 | 18 | 0 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2025/26 | April | 2026/27 | March |  |  | 0.379 |  |  |  |  | 0.379 | Y |  |  |  | 0.379 | 0.094749 | 50 | 20 | 30 | 30 | 0 | 10 | 70 | 60 | 10 | 140 | M
P41392 | Viewfield | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2021/22 | February | 58 | 36 | 18 | 4 | 288 | 222 | 48 | 18 | 36 | 0 | 24 | 12 | 0 | 0 | 0 | 18 | 0 | 8 | 0 | 0 | 10 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 37.93% | 6.897% | SR | D&B | 2024/25 | April | 2026/27 | October | 4.4191 | [6 empty] | 4.4191 | Y |  | 0.7 | 0.039 | 5.1581 | 0.088933 | 50 | 20 | 80 | 70 | 0 | 20 | 70 | 150 | 20 | 240 | H
P41364 | Westwood Park | Glenrothes | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2023/24 | August | 42 | 25 | 13 | 4 | 204 | 121 | 67 | 16 | 25 | 0 | 11 | 7 | 7 | 0 | 0 | 13 | 0 | 8 | 0 | 0 | 5 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 40.48% | 9.524% | SR | D&B | 2023/24 | August | 2024/25 | January | 3.653 | 0.059394 | [5 empty] | 3.7124 | Y |  | 0.6 | 0.0357 | 4.3481 | 0.10353 | 50 | 20 | 80 | 70 | 0 | 20 | 70 | 150 | 20 | 240 | H
P43857 | Toll Road Phase 3 | Guardbridge | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2029/30 | January | 0 | 0 | 0 | 0 | 0 | 85 | 36 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | January | 2031/32 | April | 0.85609 |  |  |  |  | 2.114 |  | 2.9701 |  |  |  |  | 2.9701 | 0.099003 | 30 | 50 | 50 | 30 | 0 | 20 | 80 | 80 | 20 | 180 | H | 30 units to be delivered | 30
P41315 | Chapel Place MS | High Valleyfield | West Fife Villages | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 3 | 0 | 0 | 3 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | [5 empty] | 0.28425 |  | 0.28425 | Y |  |  |  | 0.28425 | 0.094749 | 40 | 10 | 50 | 10 | 20 | 30 | 50 | 60 | 50 | 160 | M
T36239 | Echobank | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KI | 2029/30 | September | 12 | 12 | 0 | 0 | 50 | 50 | 0 | 0 | 12 | 0 | 10 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2029/30 | September | 2029/30 | March | [5 empty] | 0.832 |  | 0.832 |  |  |  |  | 0.832 | 0.069333 | 40 | 20 | 0 | 10 | 0 | 10 | 60 | 10 | 10 | 80 | L
P41447 | Fraser Avenue Phase 3 - SR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KHA | 2025/26 | October | 31 | 22 | 6 | 3 | 128 | 91 | 24 | 13 | 22 | 0 | 12 | 8 | 2 | 0 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 29.03% | 9.677% | SR | D&B | 2025/26 | October | 2027/28 | November |  | 1.7 | 2.518 |  |  |  |  | 4.218 | Y |  |  |  | 4.218 | 0.13606 | 40 | 20 | 0 | 30 | 20 | 20 | 60 | 30 | 40 | 130 | L
P47095 | Fraser Avenue Phase 3 - MMR | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | No | KHA | KHA | 2025/26 | October | 13 | 13 | 0 | 0 | 58 | 58 | 0 | 0 | 13 | 0 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2025/26 | October | 2027/28 | November |  | 0.3 | 1.081 |  |  |  |  | 1.381 | Y |  |  |  | 1.381 | 0.10623 | 40 | 20 | 0 | 30 | 20 | 10 | 60 | 30 | 30 | 120 | L
P44511 | Prestonhill Quarry | Inverkeithing | Dunfermline & Coast | Dunfermline & West Fife | Yes | KHA | KHA | 2029/30 | October | 0 | 0 | 0 | 0 | 0 | 116 | 65 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | October | 2031/32 | March | [5 empty] | 0.25 | 3.758 | 4.008 |  |  |  |  | 4.008 | 0.089067 | 40 | 20 | 10 | 30 | 0 | 10 | 60 | 40 | 10 | 110 | L | 45 units to be delivered | 45
P41480 | Keltyhill Road | Kelty | Cowdenbeath | Dunfermline & West Fife | No | KHA | KHA | 2029/30 | August | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | August | 2030/31 | February | [5 empty] | 0.2 | 0.388 | 0.588 |  |  |  |  | 0.588 | 0.098 | 40 | 5 | 50 | 30 | 0 | 10 | 45 | 80 | 10 | 135 | M | 6 units to be delivered | 6
P45311 | Langside Crescent Phase 2B | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2024/25 | January | 20 | 11 | 8 | 1 | 111 | 50 | 56 | 5 | 11 | 0 | 5 | 6 | 0 | 0 | 0 | 8 | 0 | 2 | 0 | 2 | 4 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 45% | 5% | SR | D&B | 2024/25 | January | 2026/27 | June | 0.5 | 1.3869 | [5 empty] | 1.8869 | Y |  | 0.25 |  | 2.1369 | 0.10685 | 50 | 35 | 80 | 70 | 0 | 20 | 85 | 150 | 20 | 255 | H
P44737 | Langside Road | Kennoway | Levenmouth | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2028/29 | April | 0 | 0 | 0 | 0 | 0 | 132 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March |  |  |  |  | 2.351 | 2.351 |  | 4.702 |  |  |  |  | 4.702 | 0.097958 | 50 | 35 | 0 | 10 | 0 | 10 | 85 | 10 | 10 | 105 | L | 48 units to be delivered | 48
P40812 | Upper Forth View Phase 1 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC PSD | FC | 2028/29 | November | 0 | 0 | 0 | 0 | 0 | 123 | 37 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | November | 2030/31 | October |  |  |  |  | 1 | 1 | 1.79 | 3.79 | Y |  |  |  | 3.79 | 0.094749 | 40 | 10 | 10 | 10 | 20 | 20 | 50 | 20 | 40 | 110 | L | 40 units to be delivered | 40
P41374 | Upper Forth View Phase 2 | Kincardine | West Fife Villages | Dunfermline & West Fife | Yes | FC | FC | 2029/30 | October | 0 | 0 | 0 | 0 | 0 | 112 | 49 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | October | 2031/32 | October | [5 empty] | 0.8 | 2.99 | 3.79 | Y |  |  |  | 3.79 | 0.094749 | 40 | 10 | 10 | 10 | 20 | 20 | 50 | 20 | 40 | 110 | L | 40 units to be delivered | 40
P47609 | West of Viewforth Place / Burntisland Road | Kinghorn | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2024/25 | September | 25 | 23 | 0 | 2 | 95 | 87 | 0 | 8 | 23 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 8% | 8% | SR | D&B | 2024/25 | September | 2025/26 | January |  | 2.5502 | [5 empty] | 2.5502 | Y |  |  |  | 2.5502 | 0.10201 | 50 | 30 | 10 | 70 | 20 | 20 | 80 | 80 | 40 | 200 | M
P46176 | South of Hill View | Kinglassie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | KHA | 2023/24 | December | 45 | 32 | 13 | 0 | 195 | 143 | 52 | 0 | 32 | 0 | 15 | 15 | 2 | 0 | 0 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.89% | 0% | SR | D&B | 2023/24 | December | 2025/26 | November | 4.9106 | [6 empty] | 4.9106 | Y |  |  |  | 4.9106 | 0.10912 | 50 | 20 | 40 | 70 | 0 | 10 | 70 | 110 | 10 | 190 | H
P45415 | Fair Isle Road (OTS) (Templehall Regen Ph 1) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2022/23 | October | 10 | 4 | 4 | 2 | 65 | 24 | 32 | 9 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 60% | 20% | SR | OTS | 2022/23 | October | 2025/26 | September | 0.98332 | [6 empty] | 0.98332 | Y |  |  | 0.027933 | 1.0113 | 0.10113 | 50 | 30 | 80 | 70 | 20 | 20 | 80 | 150 | 40 | 270 | H
P47798 | Hunter Street | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2026/27 | September | 19 | 19 |  |  | 116 | 116 | 0 | 0 | 19 | 5 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | September | 2028/29 | April |  |  | 0.7 | 0.839 |  |  |  | 1.539 |  |  |  |  | 1.539 | 0.081 | 50 | 30 | 0 | 30 | 20 | 10 | 80 | 30 | 30 | 140 | M
P44715 | Kingdom Park Phase 3 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | January | 0 | 0 | 0 | 0 | 0 | 286 | 91 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | January | 2032/33 | January | [5 empty] | 0.2 | 8.43 | 8.63 | Y |  |  |  | 8.63 | 0.099195 | 50 | 30 | 40 | 30 | 20 | 20 | 80 | 70 | 40 | 190 | H | 87 units to be delivered | 87
P41474 | Kirkcaldy SW SDA Phase 1 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | January | 0 | 0 | 0 | 0 | 0 | 165 | 52 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | January | 2031/32 | December | [5 empty] | 0.2 | 4.5374 | 4.7374 | Y |  |  |  | 4.7374 | 0.094749 | 50 | 30 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140 | M | 50 units to be delivered | 50
P46106 | Templehall Regeneration Phase 2 | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2027/28 | July | 12 | 8 | 0 | 4 | 44 | 24 | 0 | 20 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 33.33% | 33.33% | SR | FC BS | 2027/28 | July | 2028/29 | July |  |  |  | 1.137 |  |  |  | 1.137 | Y |  |  |  | 1.137 | 0.094749 | 50 | 30 | 0 | 30 | 20 | 20 | 80 | 30 | 40 | 150 | M
P46177 | Templehall Regeneration Phase 3 (MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2027/28 | July | 12 | 12 | 0 | 0 | 48 | 48 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | July | 2028/29 | July |  |  |  | 0.831 |  |  |  | 0.831 | Y |  |  |  | 0.831 | 0.06925 | 50 | 30 | 0 | 30 | 20 | 10 | 80 | 30 | 30 | 140 | M
P44714 | The Postings (FC) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC PSD | FC | 2027/28 | April | 50 | 34 | 12 | 4 | 109 | 75 | 26 | 8 | 34 | 0 | 14 | 16 | 4 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 32% | 8% | SR | D&B | 2027/28 | April | 2028/29 | May |  |  |  | 2 | 1.7374 |  |  | 3.7374 | Y |  | 1 |  | 4.7374 | 0.094749 | 50 | 30 | 0 | 30 | 20 | 20 | 80 | 30 | 40 | 150 | M
P47796 | The Postings (KHA SR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KHA | 2027/28 | October | 25 | 15 | 8 | 2 | 143 | 68 | 67 | 8 | 15 | 0 | 7 | 8 | 0 | 0 | 0 | 8 | 0 | 3 | 3 | 1 | 1 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 40% | 8% | SR | D&B | 2027/28 | October | 2029/30 | March |  |  |  | 1.187 | 1.187 |  |  | 2.374 |  |  |  |  | 2.374 | 0.09496 | 50 | 30 | 0 | 30 | 20 | 20 | 80 | 30 | 40 | 150 | M
P47797 | The Postings (KHA MMR) | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | KHA | KI | 2027/28 | October | 25 | 25 | 0 | 0 | 80 | 80 | 0 | 0 | 25 | 10 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2027/28 | October | 2029/30 | March |  |  |  | 1.012 | 1.012 |  |  | 2.024 |  |  |  |  | 2.024 | 0.08096 | 50 | 30 | 0 | 30 | 20 | 20 | 80 | 30 | 40 | 150 | M
P41320 | Union Street MS | Kirkcaldy | Kirkcaldy | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2028/29 | May | 3 | 0 | 0 | 3 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2028/29 | June | 2028/29 | December |  |  |  |  | 0.28425 |  |  | 0.28425 | Y |  |  |  | 0.28425 | 0.094749 | 50 | 30 | 50 | 10 | 20 | 30 | 80 | 60 | 50 | 190 | H
P43196 | Pitlethie Road Phase 1 (CB) | Leuchars | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2023/24 | March | 49 | 40 | 8 | 1 | 219 | 183 | 32 | 4 | 40 | 0 | 21 | 17 | 2 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 18.37% | 2.041% | SR | D&B | 2024/25 | March | 2025/26 | November | 0.784 | [6 empty] | 0.784 |  | 5.316 | 0.08175 | 0.08175 | 6.2635 | 0.12783 | 30 | 50 | 80 | 70 | 0 | 20 | 80 | 150 | 20 | 250 | H
P43915 | Pitlethie Road Phase 2 | Leuchars | St Andrews | St Andrews & East Fife | No | KHA | KHA | 2028/29 | April | 0 | 0 | 0 | 0 | 0 | 132 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | April | 2030/31 | March | 1.4478 |  |  |  | 3.1565 |  |  | 4.6043 |  |  |  |  | 4.6043 | 0.10009 | 30 | 50 | 50 | 30 | 0 | 20 | 80 | 80 | 20 | 180 | H | 46 units to be delivered | 46
P45421 | Park Drive (EHDP) | Leven | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2025/26 | November | 29 | 19 | 6 | 4 | 128 | 92 | 24 | 12 | 19 | 0 | 7 | 8 | 4 | 0 | 0 | 6 | 0 | 3 | 3 | 0 | 0 | 0 | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 34.48% | 13.79% | SR | D&B | 2025/26 | November | 2027/28 | September | 0.387 | 0.8 | 1.2504 |  |  |  |  | 2.4374 | Y |  | 0.4 | 0.0098 | 2.8472 | 0.098179 | 50 | 35 | 50 | 30 | 20 | 20 | 85 | 80 | 40 | 205 | H
T36562 | Hall Street (Fab-tek Phase 1) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2025/26 | April | 47 | 37 | 10 | 0 | 145 | 109 | 36 | 0 | 37 | 19 | 17 | 0 | 1 | 0 | 0 | 10 | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21.28% | 0% | SR | D&B | 2025/26 | September | 2027/28 | November | 0.40935 | 2.097 | 1.897 |  |  |  |  | 4.4033 | Y |  |  |  | 4.4033 | 0.093688 | 40 | 5 | 80 | 30 | 20 | 10 | 45 | 110 | 30 | 185 | M
P41385 | Jenny Gray House (EC housing) | Lochgelly | Cowdenbeath | Dunfermline & West Fife | No | FC | FC | 2021/22 | January | 44 | 0 | 30 | 14 | 128 | 0 | 82 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 18 | 10 | 2 | 0 | 0 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 100% | 31.82% | SR | D&B | 2024/25 | August | 2026/27 | December | 3.3519 | [6 empty] | 3.3519 | Y |  |  |  | 3.3519 | 0.07618 | 40 | 5 | 80 | 70 | 0 | 30 | 45 | 150 | 30 | 225 | H
P45778 | New Flockhouse | Lochore | Cowdenbeath | Dunfermline & West Fife | No | FC PSD | FC | 2022/23 | February | 51 | 34 | 14 | 3 | 200 | 144 | 44 | 12 | 34 | 2 | 22 | 8 | 2 | 0 | 0 | 14 | 6 | 8 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 33.33% | 5.882% | SR | D&B | 2022/23 | December | 2026/27 | September | 4.2308 | [6 empty] | 4.2308 | Y |  |  | 0.00815 | 4.2389 | 0.083116 | 40 | 5 | 80 | 70 | 0 | 20 | 45 | 150 | 20 | 215 | H
P47799 | Rosewell Drive | Lochore | Cowdenbeath | Dunfermline & West Fife | No | KHA | OVHA | 2026/27 | August | 15 | 10 | 4 | 1 | 49 | 26 | 19 | 4 | 10 | 8 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 33.33% | 6.667% | SR | D&B | 2026/27 | August | 2028/29 | May |  |  | 1.5 |  |  |  |  | 1.5 |  |  |  |  | 1.5 | 0.1 | 40 | 5 | 50 | 10 | 20 | 10 | 45 | 60 | 30 | 135 | M
P41449 | Durham Wynd Phase 2 | Lower Largo | Largo & East Neuk | St Andrews & East Fife | Yes | KHA | KHA | 2028/29 | April | 17 | 10 | 6 | 1 | 70 | 44 | 26 | 0 | 10 | 0 | 7 | 3 | 0 | 0 | 0 | 6 | 0 | 5 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 41.18% | 5.882% | SR | D&B | 2028/29 | April | 2029/30 | February |  |  |  |  | 1.665 |  |  | 1.665 |  |  |  |  | 1.665 | 0.097941 | 30 | 25 | 10 | 30 | 0 | 20 | 55 | 40 | 20 | 115 | L
P47096 | Land to North of Lumphinnans (LPH002 &003) | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | KHA | KHA | 2028/29 | January | 0 | 0 | 0 | 0 | 0 | 59 | 32 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2028/29 | January | 2030/31 | June |  |  |  |  | 0.25 | 1.709 |  | 1.959 | Y |  |  |  | 1.959 | 0.09795 | 40 | 5 | 0 | 10 | 0 | 20 | 45 | 10 | 20 | 75 | L | 20 units to be delivered | 20
P44711 | Lochgelly Road LPH001 | Lumphinnans | Cowdenbeath | Dunfermline & West Fife | Yes | FC PSD | FC | 2021/22 | March | 97 | 72 | 19 | 6 | 478 | 356 | 100 | 22 | 72 | 0 | 25 | 26 | 21 | 0 | 0 | 19 | 0 | 14 | 0 | 0 | 3 | 2 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 25.77% | 6.186% | SR | D&B | 2022/23 | April | 2026/27 | September | 6.9498 | [6 empty] | 6.9498 | Y |  | 1.65 |  | 8.5998 | 0.088658 | 40 | 5 | 80 | 70 | 20 | 20 | 45 | 85 | 40 | 170 | M
P44710 | Haig Business Park | Markinch | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2027/28 | April | 25 | 18 | 6 | 1 | 113 | 82 | 26 | 5 | 18 | 0 | 8 | 8 | 2 | 0 | 0 | 6 | 0 | 4 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 28% | 4% | SR | D&B | 2027/28 | April | 2028/29 | June |  |  |  | 1.7 | 0.66873 |  |  | 2.3687 | Y |  |  |  | 2.3687 | 0.094749 | 50 | 20 | 0 | 10 | 0 | 20 | 70 | 10 | 20 | 100 | L
P45416 | Methilhaven Road (Former Care Home) | Methil | Levenmouth | Kirkcaldy, Glenrothes & Central | No | FC | FC | 2026/27 | April | 40 | 28 | 9 | 3 | 196 | 140 | 43 | 13 | 28 | 0 | 12 | 11 | 5 | 0 | 0 | 9 | 0 | 6 | 2 | 0 | 1 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 30% | 7.5% | SR | D&B | 2026/27 | April | 2027/28 | January |  |  | 1.5 | 1.4916 |  |  |  | 2.9916 | Y |  | 0.8 |  | 3.7916 | 0.09479 | 50 | 35 | 50 | 30 | 20 | 20 | 85 | 80 | 40 | 205 | H
P46178 | Main Street | Milton of Balgonie | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2026/27 | November | 6 | 4 | 1 | 1 | 28 | 20 | 4 | 4 | 4 | 0 | 1 | 2 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 33.33% | 16.67% | SR | D&B | 2026/27 | November | 2027/28 | July |  |  | 0.588 |  |  |  |  | 0.588 |  |  |  |  | 0.588 | 0.098 | 50 | 20 | 10 | 30 | 0 | 20 | 70 | 40 | 20 | 130 | L
P40205 | North of Cupar Road | Newburgh | Tay Coast | Cupar & North West Fife | Yes | FC PSD | FC | 2023/24 | January | 34 | 28 | 5 | 1 | 158 | 130 | 24 | 4 | 28 | 0 | 12 | 14 | 2 | 0 | 0 | 5 | 0 | 4 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 17.65% | 2.941% | SR | D&B | 2024/25 | May | 2026/27 | May | 1.6452 | [6 empty] | 1.6452 | Y |  | 1.8 | 0.013 | 3.4582 | 0.10171 | 20 | 40 | 30 | 70 | 0 | 10 | 60 | 100 | 10 | 170 | M
P47777 | Boat Brae (Retirement Housing) | Newport | Tay Coast | Cupar & North West Fife | No | FC | FC | 2026/27 | September | 23 | 0 | 19 | 4 | 64 | 0 | 54 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 11 | 8 | 0 | 0 | 0 | 0 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 100% | 17.39% | SR | D&B | 2026/27 | September | 2027/28 | March |  |  | 1 | 0.57923 |  |  |  | 1.5792 |  |  | 0.6 |  | 2.1792 | 0.094749 | 20 | 40 | 0 | 30 | 20 | 30 | 60 | 30 | 50 | 140 | M
P46107 | James Street | Pittenweem | Largo & East Neuk | St Andrews & East Fife | Yes | FC PSD | FC | 2026/27 | October | 6 | 6 | 0 | 0 | 26 | 26 | 0 | 0 | 6 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2026/27 | October | 2027/28 | October |  |  | 0.568 |  |  |  |  | 0.568 | Y |  |  |  | 0.568 | 0.094667 | 30 | 25 | 0 | 10 | 0 | 20 | 55 | 10 | 20 | 85 | L
P43399 | Station Court | Pittenweem | Largo & East Neuk | St Andrews & East Fife | No | KHA | KHA | 2023/24 | January | 29 | 21 | 7 | 1 | 132 | 96 | 32 | 4 | 21 | 0 | 11 | 8 | 2 | 0 | 0 | 7 | 0 | 6 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 27.59% | 3.448% | SR | D&B | 2023/24 | January | 2025/26 | April | 3.6852 | [6 empty] | 3.6852 |  |  |  |  | 3.6852 | 0.12708 | 30 | 25 | 80 | 70 | 0 | 20 | 55 | 150 | 20 | 225 | H
P43422 | Brankholm Brae Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | April | 0 | 0 | 0 | 0 | 0 | 125 | 40 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | April | 2030/31 | December | [5 empty] | 0.2 | 3.524 | 3.724 |  |  |  |  | 3.724 | 0.098 | 40 | 20 | 50 | 30 | 0 | 20 | 60 | 80 | 20 | 160 | M | 38 units to be delivered | 38
P41378 | Castle Road (Recreational Park) | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2025/26 | January | 30 | 14 | 13 | 3 | 124 | 84 | 32 | 8 | 14 | 0 | 6 | 6 | 2 | 0 | 0 | 13 | 0 | 5 | 2 | 0 | 6 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 53.33% | 10% | SR | D&B | 2025/26 | January | 2027/28 | September | 0.41 |  | 1.632 | 0.2 |  |  |  | 2.242 | Y |  | 0.6 |  | 2.842 | 0.094733 | 40 | 20 | 50 | 30 | 0 | 30 | 60 | 80 | 30 | 170 | M
P47780 | Primrose Lane | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | Yes | FC PSD | FC | 2025/26 | April | 36 | 24 | 10 | 2 | 168 | 112 | 48 | 8 | 24 | 0 | 12 | 8 | 4 | 0 | 0 | 10 | 0 | 8 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 33.33% | 5.556% | SR | D&B | 2025/26 | April | 2026/27 | October |  | 1 | 2.011 |  |  |  |  | 3.011 |  |  | 0.4 |  | 3.411 | 0.094749 | 40 | 20 | 30 | 30 | 0 | 20 | 60 | 60 | 20 | 140 | M
P43424 | Whinnyburn Phase 1 | Rosyth | Dunfermline & Coast | Dunfermline & West Fife | No | FHG | FHG | 2029/30 | June | 0 | 0 | 0 | 0 | 0 | 83 | 26 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | August | 2030/31 | August | [5 empty] | 0.3 | 2.15 | 2.45 |  |  |  |  | 2.45 | 0.098 | 40 | 20 | 50 | 10 | 0 | 20 | 60 | 60 | 20 | 140 | M | 25 units to be delivered | 25
P41318 | Forgan Place (Prev Shoolbraids) MS | St Andrews | St Andrews | St Andrews & East Fife | No | FC | FC | 2029/30 | April | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | April | 2030/31 | December | [5 empty] | 0.1895 |  | 0.1895 | Y |  |  |  | 0.1895 | 0.094749 | 30 | 50 | 50 | 10 | 20 | 30 | 80 | 60 | 50 | 190 | H | 2 units to be delivered | 2
P43392 | Kilrymont Road | St Andrews | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2029/30 | April | 0 | 0 | 0 | 0 | 0 | 101 | 38 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | April | 2030/31 | December | [5 empty] | 0.2 | 2.832 | 3.032 | Y |  |  |  | 3.032 | 0.09475 | 30 | 50 | 30 | 30 | 0 | 20 | 80 | 60 | 20 | 160 | M | 32 units to be delivered | 32
P41478 | North Haugh Phase 1 (STA001 North) | St Andrews | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2029/30 | April | 0 | 0 | 0 | 0 | 0 | 132 | 42 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | January | 2030/31 | March | [5 empty] | 0.2 | 3.59 | 3.79 | Y |  |  |  | 3.79 | 0.094749 | 30 | 50 | 10 | 10 | 20 | 20 | 80 | 20 | 40 | 140 | M | 40 units to be delivered | 40
P41507 | Younger Gardens Ph2 (STA001 South) - MMR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KI | 2024/25 | May | 29 | 29 | 0 | 0 | 116 | 116 | 0 | 0 | 29 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2024/25 | July | 2025/26 | September |  | 2.3879 | [5 empty] | 2.3879 |  |  |  |  | 2.3879 | 0.082342 | 30 | 50 | 40 | 70 | 0 | 10 | 80 | 110 | 10 | 200 | H
P45409 | Younger Gardens Ph2 (STA001 South) - SR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KHA | 2024/25 | May | 12 | 8 | 4 | 0 | 57 | 35 | 22 | 0 | 8 | 0 | 5 | 3 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.33% | 0% | SR | D&B | 2024/25 | July | 2025/26 | September |  | 1.468 | [5 empty] | 1.468 |  |  |  |  | 1.468 | 0.12234 | 30 | 50 | 40 | 70 | 0 | 20 | 80 | 110 | 20 | 210 | H
P47098 | Younger Gardens Ph3 (STA001 South) - MMR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KI | 2026/27 | April | 9 | 9 | 0 | 0 | 36 | 36 | 0 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | MMR 30 | D&B | 2026/27 | April | 2027/28 | March |  |  | 0.623 |  |  |  |  | 0.623 |  |  |  |  | 0.623 | 0.069222 | 30 | 50 | 40 | 70 | 0 | 10 | 80 | 110 | 10 | 200 | H
P47099 | Younger Gardens Ph3 (STA001 South) - SR | St Andrews | St Andrews | St Andrews & East Fife | Yes | KHA | KHA | 2026/27 | April | 19 | 11 | 8 | 0 | 76 | 44 | 32 | 0 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.11% | 0% | SR | D&B | 2026/27 | April | 2027/28 | March |  |  | 1.861 |  |  |  |  | 1.861 |  |  |  |  | 1.861 | 0.097947 | 30 | 50 | 40 | 70 | 0 | 20 | 80 | 110 | 20 | 210 | H
T36565 | Bonfield Park | Strathkinness | St Andrews | St Andrews & East Fife | Yes | FC PSD | FC | 2024/25 | September | 30 | 20 | 9 | 1 | 139 | 94 | 40 | 5 | 20 | 0 | 9 | 8 | 3 | 0 | 0 | 9 | 0 | 3 | 3 | 3 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 33.33% | 3.333% | SR | D&B | 2024/25 | September | 2025/26 | December |  | 2.273 | [5 empty] | 2.273 | Y |  | 1 | 0.0396 | 3.3126 | 0.11042 | 30 | 50 | 30 | 70 | 0 | 20 | 80 | 100 | 20 | 200 | H
P43391 | Cash Feus Phase 1 (EHDP) | Strathmiglo | Cupar & HOF | Cupar & North West Fife | No | FC | FC | 2029/30 | April | 14 | 10 | 2 | 2 | 43 | 32 | 6 | 5 | 10 | 0 | 8 | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 28.57% | 14.29% | SR | D&B | 2029/30 | April | 2029/30 | March | 0.34619 |  |  |  |  | 0.9803 |  | 1.3265 | Y |  |  |  | 1.3265 | 0.094749 | 20 | 45 | 50 | 10 | 20 | 30 | 65 | 60 | 50 | 175 | M
P44739 | Bell Street | Tayport | Tay Coast | Greater Dundee | No | KHA | KHA | 2029/30 | January | 0 | 0 | 0 | 0 | 0 | 116 | 80 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | January | 2033/34 | April | [5 empty] | 0.5 | 4.3 | 4.8 |  |  |  |  | 4.8 | 0.097959 | 30 | 40 | 0 | 30 | 0 | 20 | 70 | 30 | 20 | 120 | L | 49 units to be delivered | 49
P41319 | Links Road MS | Tayport | Tay Coast | Greater Dundee | No | FC | FC | 2028/29 | May | 2 | 0 | 0 | 2 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2028/29 | June | 2028/29 | December |  |  |  |  | 0.1895 |  |  | 0.1895 | Y |  |  |  | 0.1895 | 0.094749 | 30 | 40 | 50 | 10 | 20 | 30 | 70 | 60 | 50 | 180 | H
P44707 | Strathore Road - Thornton SLA Phase 1 | Thornton | Glenrothes | Kirkcaldy, Glenrothes & Central | Yes | FC PSD | FC | 2029/30 | April | 0 | 0 | 0 | 0 | 0 | 180 | 46 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | SR | D&B | 2029/30 | January | 2031/32 | March | [5 empty] | 0.4 | 4.337 | 4.737 | Y |  |  |  | 4.737 | 0.09474 | 50 | 20 | 10 | 30 | 20 | 20 | 70 | 40 | 40 | 150 | M | 50 units to be delivered | 50
P43249 | Muir Road MS | Townhill | Dunfermline & Coast | Dunfermline & West Fife | No | FC | FC | 2029/30 | April | 2 | 0 | 0 | 2 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 100% | 100% | SR | D&B | 2029/30 | April | 2029/30 | March | [5 empty] | 0.1895 |  | 0.1895 | Y |  |  |  | 0.1895 | 0.094749 | 40 | 20 | 50 | 10 | 20 | 30 | 60 | 60 | 50 | 170 | M
P46180 | The Temple | Windygates | Levenmouth | Kirkcaldy, Glenrothes & Central | Yes | KHA | GHA | 2026/27 | May | 8 | 7 | 1 | 0 | 36 | 32 | 4 | 0 | 7 | 0 | 3 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5% | 0% | SR | D&B | 2026/27 | May | 2026/27 | March |  |  | 0.784 |  |  |  |  | 0.784 | Y |  |  |  | 0.784 | 0.098 | 50 | 35 | 30 | 70 | 0 | 10 | 85 | 100 | 10 | 195 | H
[10 empty] | 2299 | 1578 | 561 | 160 | 9716 | 10719 | 3589 | 868 | 1578 | 47 | 754 | 650 | 127 | 0 | 0 | 561 | 100 | 352 | 21 | 23 | 63 | 2 | 160 | 17 | 122 | 20 | 1 | 0 | 0 | 31.36% | 6.96% | [6 empty] | 58.5667 | 38.482 | 35.679 | 31.5853 | 30.8669 | 36.4026 | 61.898 | 293.4805 |  | 7.226 | 19.7128 | 0.71375 | 321.133 | [12 empty] | 1222
[15 empty] | 21438 | 7178 | 1736

## Codes
This sheet has all the options for the dropdown lists on the main sheet. Blank rows have been left to allow extra options to be added in the future - please do not delete them.
SLP Status
17/18
18/19
19/20 | Priority
20/21 | L
21/22 | M
22/23 | H
23/24
Developer | AHP Contibution site
FC | Y
FC PSD | N
KHA
KI
FHG
OVHA
Ark HA
Link HA
Landlord
FC
FC PSD
KHA
KI
FHG (A)
OVHA
GHA
FHG
Ark HA
Link HA
LHS Area |  | HMA Area
Glenrothes |  | Dunfermline & West Fife
Kirkcaldy |  | Kirkcaldy, Glenrothes & Central
Levenmouth |  | Cupar & North West Fife
Dunfermline & Coast |  | St Andrews & East Fife
Cowdenbeath |  | Greater Dundee
West Fife Villages |  | Fife
Cupar & HOF
Largo & East Neuk
St Andrews
Tay Coast
Fife
Years
2017/18
2018/19
2019/20
2020/21
2021/22
2022/23
2023/24
2024/25
2025/26
2026/27
2027/28
2028/29
2029/30
2030/31
2031/32
2032/33
2033/34
Tenure
SR
MMR 30
MMR 5
PSR
Other
Contract Type
D&B
OTS
FC BS
Staged
SCAPE
Change Control
Add - to be approved
Removed - to be approved
Other Change - lead delivery partner
Other Change - see comments
Stage
0 - Feasibility
1 - Dev Mix & brief
2 - design, plg & acq
3 - Contract Neg/tender approval
4 - on site
5 - completed
Block
A
B
Shadow
Programmed/Potential
Programmed
Potential
Phase 4
Shadow
Below List
Phase 4 Yr 1 & 2
Phase 4 Yr 3 to 5